## Goods
Country/Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (GOODS) FOR JANUARY - DECEMBER 2021 (12 MONTHS) | [5 empty] | Exchange Rate | 380 |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Grant ID#: 60029544 |  | BASIC DATA | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation |  |  |  |  | Link to Results
Description | Package Number | Lot Number | Estimated Amount in US $ | Estimated Amount in NGN ₦ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance | Final Cost (US $) | Final Cost (NGN ₦)
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Communication and marketing. Procure and print newsletters, CEFOR annual report, postgraduate handbook, flyers, notice board, bill board, door/office tag, and self assessment of impact, as applicable | NG/CEFOR/GDS/NS/2021/01 | I | 100000 | 38000000 | National Shopping* | Post | Post | Plan | NA | NA | NA | 20/1/2021 | 3/2/2021 | NA | NA | Plan | Contract Price | 10/2/2021 | NA | 17/2/2021 | NA | Mar; Jun; Sept; Dec 2021 | Apr; Jul; Oct; Dec 2021 | Actual Cost | Actual Cost | DLI#s 2; 3; 4; 7
[8 empty] | Actual | [7 empty] | Actual
Administrative charges. Procure stationery, realms of paper, toners for printers, maintenance of internet facility and other office equipment, as well as quality fiduciary and procurement processes, as applicable | NG/CEFOR/GDS/NS/2021/02 | 2 | 50000 | 19000000 | National Shopping | Post | Post | Plan | NA | NA | NA | 20/1/2021 | 3/2/2021 | NA | NA | Plan | Contract Price | 10/2/2021 | NA | 17/2/2021 | NA | Mar; Jun; Sept; Dec 2021 | Apr; Jul; Oct; Dec 2021 | Actual Cost | Actual Cost | DLI#s 2; 3; 4; 5; 6; 7
[8 empty] | Actual | [7 empty] | Actual
Teaching aids (projectors, data services, internet connectivity) maintenance. Make up teaching aids and data services, maintenance, replacement, if any | NG/CEFOR/GDS/NCB/2021/03 | 3 | 70000 | 26600000 | NCB | Post | Post | Plan | NA | NA | 07/02/2021 | 21/02/2021 | 04/04/2021 | NA | NA | Plan | Contract Price | 11/04/2021 | 11/04/2021 | 18/04/2021 | 25/04/2021 | 24/05/2021 | 06/06/2021 | Actual Cost | Actual Cost | DLI#s 3; 4; 7
[8 empty] | Actual | [7 empty] | Actual
Books & journals. Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR, maintenance of laboratory furniture, if any | NG/CEFOR/GDS/NCB/2021/04 | 4 | 70000 | 26600000 | NCB | Post | Post | Plan | NA | NA | 07/02/2021 | 21/02/2021 | 04/04/2021 | NA | NA | Plan | Contract Price | 11/04/2021 | 11/04/2021 | 18/04/2021 | 25/04/2021 | 24/05/2021 | 06/06/2021 | Actual Cost | Actual Cost | DLI#s 3; 4; 7
[8 empty] | Actual | [7 empty] | Actual
100 kVA Diesel Generator with accessories. Procure fuel (diesel), servicing, repairs, maintenance, logistics for generator attendant, if any | NG/CEFOR/GDS/NS/2021/05 | 5 | 55000 | 20900000 | National Shopping | Post | Post | Plan | NA | NA | NA | 20/1/2021 | 3/2/2021 | NA | NA | Plan | Contract Price | 10/2/2021 | NA | 17/2/2021 | NA | Mar; Jun; Sept; Dec 2021 | Apr; Jul; Oct; Dec 2021 | Actual Cost | Actual Cost | DLI#s 1; 2; 3; 4; 5; 6; 7
[8 empty] | Actual | [7 empty] | Actual
Project vehicles (Toyota: 1no Corolla car; 1no Hiace bus). Procure fuel (petrol), servicing, repairs, maintenance | NG/CEFOR/GDS/NS/2021/06 | 6 | 36000 | 13680000 | National Shopping | Post | Post | Plan | NA | NA | NA | 20/1/2021 | 3/2/2021 | NA | NA | Plan | Contract Price | 10/2/2021 | NA | 17/2/2021 | NA | Mar; Jun; Sept; Dec 2021 | Apr; Jul; Oct; Dec 2021 | Actual Cost | Actual Cost | DLI#s 1; 2; 3; 4; 5; 6; 7
[8 empty] | Actual | [7 empty] | Actual
Laboratory equipment and associated furniture, reagents, maintenance. Make up procurement, installation and maintenance of sundry laboratory equipment with associated furniture | NG/CEFOR/GDS/NCB/2021/07 | 7 | 380000 | 144400000 | NCB | Post | Post | Plan | NA | NA | 07/02/2021 | 21/02/2021 | 04/04/2021 | NA | NA | Plan | Contract Price | 11/04/2019 | 11/04/2019 | 18/04/2019 | 25/04/2019 | 24/05/2019 | 06/06/2019 | Actual Cost | Actual Cost | DLI#s 1; 2; 3; 4; 5; 7
[8 empty] | Actual | [7 empty] | Actual
Office, e-library and classroom furniture with accessories. Make up procurement, installation and maintenance of sundry office, and e-library | NG/CEFOR/GDS/NCB/2021/08 | 8 | 90000 | 34200000 | NCB | Post | Post | Plan | NA | NA | 07/02/2021 | 21/02/2021 | 04/04/2021 | NA | NA | Plan | Contract Price | 11/04/2021 | 11/04/2021 | 18/04/2021 | 25/04/2021 | 24/05/2021 | 06/06/2021 | Actual Cost | Actual Cost | DLI#s 3; 4; 7
[8 empty] | Actual | [7 empty] | Actual
e-Procurement software. Procure and install facilities/furniture, e-procurement software/accounting software for UniPort Procurement/Accounting Unit | NG/CEFOR/GDS/DC/2021/09 | 9 | 40000 | 15200000 | Direct Contracting** | Pre- | Prior | Plan | NA | 16/3/2021 | NA | 19/3/2021 | 2/4/2021 | NA | NA | Plan | Contract Price | 9/4/2021 | 16/4/2021 | 19/4/2021 | 23/4/2021 | 30/4/2021 | 7/5/2021 | Actual Cost | Actual Cost | DLI#s 4; 6; 7
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 891000 | 338580000 |  |  |  | Plan | [7 empty] | Plan
|  |  | 0 |  |  |  |  | Actual | [7 empty] | Actual
Fill gray cells only!
KEY:
|  | * | Lots 1, 2, 5 and 6 shall be National Shopping and requires continuous / quarterly supplies, estimated to be less than NGN ₦ 2,5000,000, which is not very easy to directly quantify since needs/pages of prints, maintenance needs like feeling might vary per quarter
|  | NCB | National Competitive Bidding
|  | ** | The vendor was the contractor who designed and installed the current BPP e-Procurement software, the ACE-CEFOR wishes to adopt for centre use and the UniPort Procurement Unit for overall improved procurement process

## Works
Country/Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (WORKS) FOR JANUARY - DECEMBER 2021 (12 MONTHS) | [5 empty] | Exchange Rate | 380 |  |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Grant ID#: 60029544 |  | Basic Data | [9 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Estimated Amount in NGN ₦ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US $ | Contract Amount in NGN ₦ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost in US $ | Final Cost in NGN ₦
Norm Duration of Proc Steps | [6 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  |  | 1 wk |  | 1.5-3 wks
[7 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
CEFOR Building (external works landscaping; maintenance of facilities at building). | NG/CEFOR/WKS/ST/2021/10 | 10 | Bill of Quantities | Selective Tendering¶ | 150000 | 57000000 | Post | Post | Plan | NA | NA | NA | 18/03/2019 | 01/04/2019 | NA | NA | Plan | Contract Price | Contract Price | 08/04/2019 | NA | 16/04/2017 | 23/04/2017 | 27/05/2017 | 06/06/2017 | Actual Cost | Actual Cost
[7 empty] | Post | Post | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 150000 | 57000000 |  |  | Plan | [7 empty] | Plan | Contract Price | Contract Price | [6 empty] | Actual Cost | Actual Cost
[5 empty] | 0 | 0 |  |  | Actual | [7 empty] | Actual | 0 | 0 | [6 empty] | 0 | 0
Fill gray cells only!
¶KEY:
| 1 | To, as much as is possible, ensure work continuation coupled with difficulty in reproducing by another vendor, and since the existing contractor did not default in the first instance but, hindered by project fund source.
| 2 | Defining the exact needs of the requirements for completing the project is also very complicated, which may pose a great challenge for open tendering.
| 3 | Generally, the proposed procurement method shall help save time and money for ACE-CEFOR

## Consultants
Country/Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (CONSULTANT) FOR JANUARY - DECEMBER 2021 (12 MONTHS) | [7 empty] | Exchange Rate | 380
For Contracts under projects approved before the May 2002 Guidelines
|  | If Post-Review, No-objection Dates are not needed | [6 empty] | Request for EOI (where required)
Grant ID#: 60029544 |  | Contract Type |  |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
Description | Selection Method | Lumpsum or Time-Based | Estimated Amount in US $ | Estimated Amount in NGN ₦ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost in US $ | Final Cost in NGN ₦
Norm Duration of Proc Steps | [5 empty] | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Development Impact. Procure consulting services for independent external evaluation of impact, as well as vigorous marketing of CEFOR’s programs to national & international target audience, regional student recruitment, publicity and outreach, scientific image, as applicable. | Single Source Selection† | Lump sum | 100000 | 38000000 | Post | Plan | 18/01/2021 | 08/02/2021 |  |  |  |  | Plan | [7 empty] | Plan | 15/02/2021 | 22/02/2021 |  | 01/03/2021 | 02/03/2021 | 10/03/2021 | Plan | 17/03/2021 | 13/09/2021 | 11/10/2021
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Institutional Impact. Procure annual internet support services (NGReN; with e-resources and associated internet access & connectivity for UniPort) | Single Source Selection‡ | Lump sum | 150000 | 57000000 | Post | Plan | 18/01/2021 | 08/02/2021 |  |  |  |  | Plan | [7 empty] | Plan | 15/02/2021 | 22/02/2021 |  | 01/03/2021 | 02/03/2021 | 10/03/2021 | Plan | 17/03/2021 | 14/04/2021 | 10/05/2021
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 250000 | 95000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!
KEY:
|  | † | ACE-CEFOR has understanding with Africa Development Futures Group (a reputable international online communication, marketing and admission management solution entity) to, effectively, handle the aspect of recruiting international and regional students meeting DLI #2
|  | ‡ | It was agreed that, the ACE Project Coordinating Agency in Nigeria (National Universities Commission, NUC) was mandated to provide NgREN basic services for all the Nigerian ACEs to subscribe to the Nigerian Research and Education Network (NgREN)