## 2022CEFORWorkplan
Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR)
Institution | University of Port Harcourt |  |  | On Schedule | [11 empty] | EXCHANGE RATE: ₦411 = U.S. $1
Country | Nigeria
Center Leader | Professor Ogbonna Friday Joel |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January 01-December 31, 2022
Work Plan Activities | Description | Partner Contribution (if relevant) | 2022 Y3Q1 |  |  | 2022 Y3Q2 |  |  | 2022 Y2Q3 |  |  | 2022 Y3Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible | Contribution to DLI
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Readiness \ DLI Action: 1
Sub-Action 1a: Basic Readiness
Activity 1: Prepare Workplan | Itemise planned activities for Year 2022 | Make inputs on mutually beneficial projects | [12 empty] | 1no 2022 Work Plan | Done, annually | NA | NA | NA | Centre Leader | DLI 1
Activity 2: Prepare Procurement Plan | List potential contracts and procurements to achieve workplan | Make inputs on mutually beneficial projects | [12 empty] | 1no 2022 Procurement Plan | Done, annually | NA | NA | NA | Procurement Officer | DLI 1
Activity 3: Prepare Financial Management Manual | State financial transactions and planned disbursements for 2022 | Make inputs on mutually beneficial projects | [12 empty] | 1no 2022 Financial Management Plan | Done, annually | NA | NA | NA | Project Accountant | DLI 1
Sub-Action 1b: Full Readiness
Activity 1: Maintain ACE-CEFOR website & building | Promote visibility of Centre and her activities for Year 2022 | Help publicise Centre programmes | [12 empty] | Website and building functional | Software update and renewal | 54142 | NA | NA | Procurement Officer | DLI 1
Activity 2: Maintain Statutory Advisory Board (SAB) | Strategic meetings to ensure Centre activities remain focused | Attend meetings | [12 empty] | SAB Meetings & regional Committee training | Certification and training | 136181 | NA | NA | Centre Leader | DLI 1
Activity 3: Hold Project Implementation Meeting & Review | Necessary as part of team building and implementing project | Provide feedback for improvement | [12 empty] | 8nos Project Implementation Meetings | Including stationery purchase | 58500 | NA | NA | Centre Leader | DLI 1
Action 2: Development Impact \ DLI Action: 2
Sub-Action 2a: Self-Assessment of Development Impact
Activity 1: Conduct self-assessment of development impact | Objective internal evaluation of activities for social impact | Partners provide support with survey instruments/meetings | [12 empty] | 4nos Self-assessment Reports |  | 3000 | 10000 | Nil | Centre Leader | DLI 2.1
Activity 2: Monitoring and Evaluation of project progress | Assess annual reports from Advisory Borads | Partners provide support with survey instruments/meetings | [12 empty] | 4nos Monitoring & Evaluation Reports |  | 10000 | 33333.3333 | Nil | M & E Officer | DLI 2.1
Sub-Action 2b: Independent External Evaluation of Impact
Activity 1: Conduct independent external evaluation of impact | Independent external assessment of activities for social impact | Partners provide independent evaluation about project | [12 empty] | 1no Annual Report |  | 2000 | 6666.6667 | Nil | M & E Officer | DLI 2.2
Activity 2: Conduct tracer studies | Track graduates from Centre for employers ratings | Partners provide independent evaluation about project | [12 empty] | 1no Tracer Study |  | 5000 | 16666.6667 | Nil | M & E Officer | DLI 2.2
Activity 3: Organise Alumni homecoming for ACE-CEFOR | Opportunity to interact with CEFOR graduates for development | Partners provide independent evaluation about project | [12 empty] | 2nos Homecoming Event for Alumni |  | 10000 | 33333.3333 | Nil | Centre Leader | DLI 2.2
Action 3: Quantity of Students \ DLI Action: 3
Sub-Action 3a: Admit PhD Students
Activity 1: Advertise and admit PhD students | Place adverts in, at least, two national dailies and website | PhD students from partner departments, centres & institutes | [12 empty] | 1no Advert for national/regional PhD students | Global outreach consultancy | 67500 | 110435.6436 | 148720 | Communication Officer | DLI 3.1
Activity 2: Organise orientation for PhD students | PhD Students have firsthand information about Centre | PhD students from partner departments, centres & institutes | [12 empty] | 1no Orientation for new PhD students |  | 15000 | 24541.2541 | 148720 | Centre Leader | DLI 3.1
Activity 3: Organise modular lectures for PhD students | PhD Students undertake lectures for prescribed courses | PhD students from partner departments, centres & institutes | [12 empty] | Modular lectures for admitted PhD students |  | 63750 | 104300.33 | 148720 | Centre Leader | DLI 3.1
Activity 4: Organise project seminars for PhD students | Hold pre-data and post-data project seminars for PhD students | PhD students from partner departments, centres & institutes | [12 empty] | 2nos PhD Seminars (proposal & pre-data) |  | 24000 | 39266.0066 | 148720 | Centre Leader | DLI 3.1
Activity 5: Provide research support for PhD students | Advance research funds/grants to support PhD students projects | PhD students from partner departments, centres & institutes | [12 empty] | Funding support for eligible PhD students |  | 42000 | 68715.5116 | 148720 | Centre Leader | DLI 3.1
Activity 6: Present PhD students for defence | Hold viva voce for PhD students who have completed work | PhD students from partner departments, centres & institutes | [12 empty] | PhD students defend thesis |  | 15000 | 24541.2541 | 148720 | Centre Leader | DLI 3.1
Sub-Action 3b: Admit MSc Students
Activity 1: Advertise and admit MSc students | Place adverts in, at least, two national dailies and website | MSc students from partner departments, centres & institutes | [12 empty] | 1no Advert for national/regional MSc students | Global outreach consultancy | 4000 | 6811.8812 | 107500 | Communication Officer | DLI 3.2
Activity 2: Organise orientation for MSc students | MSc Students have firsthand information about Centre | MSc students from partner departments, centres & institutes | [12 empty] | 1no Orientation for new MSc students |  | 5000 | 8514.8515 | 107500 | Centre Leader | DLI 3.2
Activity 3: Organise modular lectures for MSc students | MSc Students undertake lectures for prescribed courses | MSc students from partner departments, centres & institutes | [12 empty] | Modular lectures for admitted MSc students |  | 21250 | 36188.1188 | 107500 | Centre Leader | DLI 3.2
Activity 4: Organise project seminars for MSc students | Hold pre-data and post-data project seminars for MSc students | MSc students from partner departments, centres & institutes | [12 empty] | 2nos MSc Seminars (proposal & pre-data) |  | 7875 | 13410.8911 | 107500 | Centre Leader | DLI 3.2
Activity 5: Provide research support for MSc students | Advance research funds/grants to support MSc students projects | MSc students from partner departments, centres & institutes | [12 empty] | Funding support for eligible MSc students |  | 20000 | 34059.4059 | 107500 | Centre Leader | DLI 3.2
Activity 6: Present MSc students for defence | Hold viva voce for MSc students who have completed work | MSc students from partner departments, centres & institutes | [12 empty] | MSc students defend dissertation |  | 5000 | 8514.8515 | 107500 | Centre Leader | DLI 3.2
Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR)
Institution | University of Port Harcourt |  |  | On Schedule | [11 empty] | EXCHANGE RATE: ₦411 = U.S. $1
Country | Nigeria
Center Leader | Professor Ogbonna Friday Joel |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January 01-December 31, 2022
Work Plan Activities | Description | Partner Contribution (if relevant) | 2022 Y3Q1 |  |  | 2022 Y3Q2 |  |  | 2022 Y2Q3 |  |  | 2022 Y3Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Sub-Action 3c: Admit Short Course Students
Activity 1: Identify and mobilise faculty members & students | Receive nominations for faculty members & students | Students come from partner departments, centres & institutes | [12 empty] | 50nos Short course participants mobilised |  | 1800 | 3128.5714 | Nil | Centre Leader | DLI 3.3
Activity 2: Organise short course | Train nominated and accepted faculty members & students | Students come from partner departments, centres & institutes | [12 empty] | 50nos Short course participants trained |  | 18000 | 31285.7143 | Nil | Centre Leader | DLI 3.3
Activity 3: Train Steering Committee members | Capacity building for Steering Committee members in Nigeria | Students come from partner departments, centres & institutes | [12 empty] | 12nos Steering Committee members trained |  | 18000 | 31285.7143 | Nil | Centre Leader | DLI 3.3
Action 4: Quality of Education & Research \ DLI Action: 4
Sub-Action 4a: Accreditation of Course(s)
Activity 1: Secure national accreditation with NUC | Secure national accreditation before international accreditation | Play key roles as industry partners in the process | [12 empty] | 1no NUC National Accreditation |  | 100000 | 100000 | Nil | Centre Leader | DLI 4.1
Activity 2: Perform self-assessment/gap analysis | Self-assessment or gap analysis for international accreditation | Play key roles as industry partners in the process | [12 empty] | 1no Self-assessment/Gap assessment |  | 100000 | 100000 | Nil | Centre Leader | DLI 4.1
Activity 3: Secure international accreditation/NREP Certification | Secure international accreditation for approved Centre course | Play key roles as industry partners in the process | [12 empty] | 1no International Accreditation/NREP |  | 300000 | 300000 | Nil | Centre Leader | DLI 4.1
Activity 4: Introduce new or review existing course(s) | Create new course or review existing course at the Centre | Play key roles as industry partners in the process | [12 empty] | 1no New/Reviewed existing course |  | 50000 | 50000 | Nil | Centre Leader | DLI 4.1
Sub-Action 4b: Conduct Applied Research in Oilfield Chemicals
Activity 1: Identify and approve applied research | Select appropriate applied research for approval and support | Partner inputs on relevant researchable area(s) | [12 empty] | 6nos innovative proposal review meetings |  | 5000 | 3481.5639 | 1518.4361 | Centre Leader | DLI 4.2
Activity 2: Provide funding support in cash and or kind | Solicit possible funding support for approved applied research | Partner inputs on relevant researchable area(s) | [12 empty] | 20nos innovative applied researches supported |  | 90000 | 62668.1494 | 27331.8506 | Centre Leader | DLI 4.2
Activity 3: Sustain recognition as Regional Centre of Expertise | Stakeholders meetings & identify innovative applied researches | Partner inputs on relevant researchable area(s) | [12 empty] | 2nos Stakeholders Meeting; 2nos Conference |  | 50000 | 34815.6386 | 15184.3614 | Procurement Officer | DLI 4.2
Activity 4: Support training, workshop/conference attendance | Fund participant to training, workshop and conference | Partner inputs on relevant researchable area(s) | [12 empty] | 20nos participants from funded projects |  | 170000 | 118373.1712 | 51626.8288 | Centre Leader | DLI 4.2
Activity 5: Prepare manuscripts & publish results | Support relevant applied research and publish quality papers | Partner inputs on relevant researchable area(s) | [12 empty] | 10nos quality applied research papers |  | 37467 | 26088.7506 | 11378.2494 | Centre Leader | DLI 4.2
Activity 6: Attend ACE Impact Project Review workshop | Steering Committee members attend approved project meetings | Partner inputs on relevant researchable area(s) | [12 empty] | 2nos Project Review Workshops attended |  | 143000 | 99572.7263 | 43427.2737 | Centre Leader | DLI 4.2
Sub-Action 4c: Complete Milestone on Infrastructure Improvement
Activity 1: Identify and contract a qualified vendor | Place advert or notice for interested vendors to apply | Partners provide inputs to project identification/design | [12 empty] | 2nos Contracts awarded for information |  | 20000 | 27272.7273 | Nil | Procurement Officer | DLI 4.3
Activity 2: Initiate and complete Milestone 1 (external works) | Award and implement contract for external works at CEFOR | Partners provide inputs to project identification/design | [12 empty] | External works and scoping completed | Fix common external facilities | 100000 | 136363.6364 | Nil | Procurement Officer | DLI 4.3
Activity 3: Initiate and complete Milestone 2 (office extension) | Award and implement office extension at CEFOR | Partners provide inputs to project identification/design | [12 empty] | 1no mini-lab, canteen and body-friendly room | Canteen & baby-friendly room | 100000 | 136363.6364 | Nil | Procurement Officer | DLI 4.3
Action 5: Relevance of Education & Research \ DLI Action: 5
Sub-Action 5a: Generate External Revenue
Activity 1: Secure external funding from regional sources | Amount of grant secured from external sources in the region | Grants / donations from TotalEnergies & IFP School, France | [12 empty] | External revenue generated (regional) |  | 74600 | 419600 | 331520 | Centre Leader | DLI 5.1
Activity 2: Secure external funding from national sources | Amount of grants secured from external sources in Nigeria | National grants by CEFOR and partners (INRES, COHSE) | [12 empty] | External revenue generated (national) | About $72,870 CEFOR IGR | 25400 | 280400 | 377781 | Centre Leader | DLI 5.1
Sub-Action 5b: Organise 1-Month Internships
Activity 1: Organise Sectoral Advisory Board meeting | Convene SAB meeting for CEFOR | Partners participate in the meetings | [12 empty] | 1no Sectoral Advisory Board meeting |  | 5000 | 7592.2938 | Nil | Centre Leader | DLI 5.2
Activity 2: Organise International Scientific Advisory Board | Convene International Scientific Advisory Board meeting | Partners participate in the meetings | [12 empty] | 1no International Scientific Advisory Borad |  | 8500 | 12906.8995 | Nil | Centre Leader | DLI 5.2
Activity 3: Assign and post qualified interns to relevant industry | Enter MoU & place students on 1-month industrial internship | Partners participate in the meetings and training of interns | [12 empty] | 30nos students undertake 1-month internship |  | 39185 | 59500.8067 | Nil | Industry Liaison Officer | DLI 5.2
Sub-Action 5c: Technology Incubation & Commercialisation Process
Activity 1: Identify and review technology for incubation | Appraise positive results from ongoing or completed researches | Partners support with industry relevant researchable areas | [12 empty] | Technology for innovation identified | Appraise research results | 220000 | 220000 | Nil | Centre Leader | DLI 5.3
Activity 2: Initiate patenting process for commercialisation | Patent or commercialise good quality research outputs | Partners support with industry relevant researchable areas | [12 empty] | Commence patent & commercialisation process | Commercialise research results | 660000 | 660000 | Nil | Centre Leader | DLI 5.3
Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR)
Institution | University of Port Harcourt |  |  | On Schedule | [11 empty] | EXCHANGE RATE: ₦411 = U.S. $1
Country | Nigeria
Center Leader | Professor Ogbonna Friday Joel |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January 01-December 31, 2022
Work Plan Activities | Description | Partner Contribution (if relevant) | 2022 Y3Q1 |  |  | 2022 Y3Q2 |  |  | 2022 Y2Q3 |  |  | 2022 Y3Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 6: Timeliness & Quality of Fiduciary Management \ DLI Action: 6
Activity 1: Prepare fiduciary report | Prepare and submit fiduciary report | Not relevant | [12 empty] | 1no fiduciary report submitted |  | 15000 | 45000 | NA | Project Accountant | DLI 6.1
Activity 2: Conduct oversight internal audit by committee | Prepare and submit Internal Audit Report | Not relevant | [12 empty] | 1no Internal Audit Report submitted |  | 15000 | 30000 | NA | Project Auditor | DLI 6.2
Activity 3: Publish centre expenditure on website | Publish Centre’s Expenditure Report on website | Not relevant | [12 empty] | 1no Expenditure Report placed on website |  | 15000 | 45000 | NA | M & E Officer | DLI 6.3
Activity 4: Prepare procurement plan | Publish Centre’s Procurement Report on website | Not relevant | [12 empty] | 1no Procurement Report placed on website |  | 15000 | 30000 | NA | Procurement Officer | DLI 6.4
Action 7: Institutional Impact \ DLI Action: 7
Sub-Action 7a: UniPort university-wide regional strategy
Activity 1: Engage stakeholders for MoU / developing strategy | Produce strategy document with relevant stakeholders | Partners make inputs to MoU and endorse | [12 empty] | 1no New/Reviewed MoU live |  | 6250 | Nil | NA | Centre Leader | DLI 7.1
Activity 2: Prepare and publish university-wide strategy book | Produce and circulate university-wide strategy document | Partners make inputs to MoU and endorse | [12 empty] | Initiate university-wide strategy document | Engage stakeholders for buy-in | 10000 | Nil | NA | Centre Leader | DLI 7.1
Sub-Action 7b: Meet digital skill requirements for UniPort graduates
Activity 1: Identify students/graduates with digital skills gap | Identified students/graduates mobilised for training | Make inputs to training material & serve as resource persons | [12 empty] | Identify students/graduates for digital skills gap |  | 10000 | 10000 | NA | M & E Officer | DLI 7.2
Activity 2: Train selected students/graduates on digital skills | Train selected students/graduates for better digital skills | Make inputs to training material & serve as resource persons | [12 empty] | Train students/graduates on digital skills |  | 50000 | 50000 | NA | M & E Officer | DLI 7.2
Sub-Action 7c: Institutional International Accreditation & ISO Certification
Activity 1: Conduct gap assessment or self-evaluation exercise | Subject quality program(s) for national accreditation | Partners participate in the process | [12 empty] | Initiate Institutional NUC Accreditation process |  | 25000 | 25000 | Nil | Centre Leader | DLI 7.3
Activity 2: Initiate international accreditation /ISO certification | Institution face international accreditation & ISO Certification | Partners participate in the process | [12 empty] | Initiate ISO Certification process |  | 50000 | 50000 | Nil | Centre Leader | DLI 7.3
Sub-Action 7d: PASET Benchmarking & Intervention Plan
Activity 1: Apply for PASET Benchmarking exercise | Centre campaigns for PASET organised program | Partners participate in the process | [12 empty] | 1no PASET Benchmarking Report |  | 35000 | 35000 | Nil | Centre Leader | DLI 7.4
Activity 2: Participate and submit PASET Intervention Plan | Centre participates in PASET call for grants application(s) | Partners participate in the process | [12 empty] | 1no Application for PASET support grant |  | 15000 | 15000 | Nil | Centre Leader | DLI 7.4
Sub-Action 7e: Milestone on Institutional Impact
Activity 1: Engage UniPort Foundation for agreed intervention | Centre supports UniPort to implement agreed | Partners participate in the process | [12 empty] | Identify university project like strategic plan | UniPort Foundation approval | 10000 | 10000 | Nil | Centre Leader | DLI 7.5
Activity 2: Facilitate a university-wide function in UniPort | Centre to provide support for a university-wide function | Partners participate in the process | [12 empty] | 1no university-wide function implemented | Beneficial to the University | 90000 | 90000 | Nil | Centre Leader | DLI 7.5
Sub-Action 7f: ICT for Innovation in Teaching & Research
Activity 1: Conduct scoping study of areas to extend ICT to | Centre to access areas yet, to enjoy internet cover and include | Partners participate in the process | [12 empty] | University sections for ICT extension identified |  | 10000 | 30000 | Nil | Centre Leader | DLI 7.6
Activity 2: Extend ICT for teaching and research to need areas | Extend ICT facility including NgREN to all parts on UniPort | Partners participate in the process | [12 empty] | ICT facilities provided at new locations |  | 90000 | 270000 | Nil | Procurement Officer | DLI 7.6
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus
Note on V45: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus
Note on V84: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus