## General Work Plan
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: WORK PLAN FOR JANUARY - DECEMBER 2022 (12 MONTHS)
WORK PLAN (JANUARY - DECEMBER 2022)
Year 2022
Activity No | ACTIVITY | SUB-ACTIVITY | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT | January - December 2022
[7 empty] | J | F | M | A | M | J | J | A | S | O | N | D
[7 empty] | A | E | A | P | A | U | U | U | E | C | O | E
[7 empty] | N | B | R | R | Y | N | L | G | P | T | V | C
1 | Accreditation/Gap analysis | International accreditation gap analysis, self evaluation/close-ups | This will create easy platform for collaboration, regional students enrolment and enhance visibility and marketability | 100000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa wtih, globally, recognised postgraduate programmes and global clients base | Centre Leader / Deputy Centre Leader
2 | Communication and marketing | Newsletters/advertisement | This is necessary for centre publicity, public awareness and stakeholders information, engagement, visibility and marketing | 40000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa with wider visibility, acceptance and patronage within and outside West and Central Africa | Communication / M&E / Procurement Officers
3 | Students and faculties support | Scholarship, research, publications, supervision, internship, invite visiting scholars, conferences, seminars and workshops | Attend conferences/seminars/workshops; Communicate research findings; Students/Faculty development, host visiting scholars, Research and innovation and publicity | 250000 | Increased capabilities of faculties and students in the sub-region to adopt global best practices in research and training in Petroleum and related disciplines. and quality postgraduate education, knowledge transfer and internship programmes | Centre Leader
4 | National Registry of Environmental Professionals (NREP), USA certification | Training and certification by the National Registry of Environmental Professionals (NREP), USA | Training and certification by NREP shall make the certified candidates very marketable and employable upon graduation; secure NREP certification for our students and faculties for improved employability | 70000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa and more protected environments and better environmental consciousness among industry players | Centre Leader
5 | Vigorious online marketing and campaigns within and outside region | Embark on / sustain exploratory and consolidation trips to institutions of interest and online contacts within and outside Nigeria | Increased publicity and patronage to attain greater regional relevance for the ACE-CEFOR project, Solicit patronage from potential partners and establish new partnerships | 70000 | More prospective partners and clients aware of ACE-CEFOR products and services for Centre sustainability | Centre Leader
6 | Sustain recognition as Regional Centre of Expertise (RCE) | Hold stakeholders meetings; develop and submit concepts/proposals for funding; embark on sustainable development projects | Promotion of science education at all levels will enhance attainment of the UN Post-2015 Sustainable Development Goals (SDGs), better responses to socio-economic needs, and greener production processes in the petroleum and environmental studies sectors | 50000 | Increased knowledge on new thinking in SDGs implementation for adoption of green technologies and chemicals for eco-friendly industry operations | Procurement
7 | Negotiate/sign memoranda, and commitment to partners | Follow up with identified partners to firm up partnership, support multi-year annual institutional membership dues to AAU, ACU, RUFORUM, etc | Entering into memorandum of understanding will strengthen project, increase regional presence and good collaboration, cover costs for travels, annual subscriptions for regional partnership to enhance regional students enrolment | 70000 | Increased preference for ACE-CEFOR and sustainability of ACE-CEFOR | Centre Leader / Deputy Centre Leader
8 | Attend ACE meetings | Participate at ACE approved meetings | Visibility and progress report, Highlight performance and make presentations | 143000 | Better informed staff for high staff productivity and greater project reach out | Centre Leader
9 | Organise short courses, attend short courses by steering committee members/other stakeholders | Hold/attend short courses | Improved service delivery and performance, enhance capacity of steering committee members, carry out consultancy services for the oil and gas industry | 150000 | Improved staff capacity to organise trainings and deliver modules for wider ACE-CEFOR/UniPort visibility, acceptance and patronage within and outside West and Central Africa | Centre Leader
10 | Administrative charges (bank transactions; steering committee meetings; bills, stationery, realms of paper, toners for printers, maintenance of internet facility and other office equipment, as well as quality fiduciary and procurement processes, as applicable | Day-to-day running of the Centre and coordination of all activities | This will ensure Holistic and strategic management of the Centre, ensure coordinated project implementation and delivery, support maintenance logistics for ACE-CEFOR, etc | 70000 | Increased awareness about institutional benefits of improved financial and procurement processes for more public and private partners working with ACE-CEFOR and UniPort | Centre Leader
11 | Teaching aids (MIS/LMS equipment like, projectors, data services, internet connectivity) maintenance | Make up teaching aids and data services, maintenance, replacement, if any | This will enable the Centre provide efficient learning environment, facilitate efficient course delivery | 150000 | Improved preference for teaching, learning and research for lifelong learning by students and faculty | Procurement
12 | Books & journals. Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR/partner units, maintenance of laboratory furniture, if any | Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR/partner units, maintenance of laboratory furniture | This will ease learning challenges, enhance access to print literature, promote patenting in university, etc, enhance teaching, learning and research by faculties and students | 70000 | Preference for use of ACE-CEFOR library by students and faculty for increased scholarship, innovative research, publication and patenting | Procurement
13 | 200 kVA Diesel Generator with transformer and accessories | Buy soundproof gen set; transformer; fuelling (diesel), servicing, repairs, maintenance, logistics for generator attendant, if any | Back-up power failure to enhance teaching, learning and research by faculties and students, enhance teaching, learning and research environment | 80000 | Increased motivation of staff and faculty for improved staff and faculty productivity | Procurement
14 | Project vehicles | Procure 1no Project car, 1no 30-seater bus, fuelling (petrol), servicing, repairs, maintenance, etc | Provides transportation logistics for centre leader and other steering committee members as well as faculties and students on field tours and visits | 200000 | Improved job satisfaction, enhanced capacity to secure accreditation for increased productivity | Procurement
15 | Laboratory equipment and associated furniture, reagents, maintenance/lab staff training, IEC materials to support COVID-19 awareness campaign | Make up procurement, installation and maintenance of sundry laboratory equipment with associated furniture | This will lead to proper handling of procured equipment, repair laboratory space in readiness for receiving equipment, health training materials | 240000 | Improved preference for teaching, learning and research for lifelong learning by students and faculties, better informed staff and stakeholders for safety and wellness | Procurement
16 | Office, e-library and NgREN internet support for partner centres/departments/units in UniPort | Installation/support annual subscriptions like NgREN, mHealth, etc | This is necessary to prepare offices, e-library and classrooms for better working environment, make CEFOR building fully functional for enhanced service delivery | 200000 | Improved preference for teaching, learning and research for lifelong learning by students and faculties | Procurement
17 | e-Procurement software. Procure and install facilities/furniture, e-procurement/e-accounting/e-auditting software for ACE-CEFOR Procurement/Accounting/Audit Units | Procure and install facilities / furniture, e-procurement software and project management software | This shall ensure increased timely and transparent institutional procurement process with improved value for money | 55000 | Improved e-procurement knowledge by procurement staff for effective and efficient institutional Procurement Unit | Procurement
18 | CEFOR Building (external works landscaping, maintenance of facilities in building). Details include a mini-laboratory, a canteen and a baby-friendly centre, road safety signs, CCTV gadgets, refuse receptacles and cleaning equipment | Complete building to house extension of CEFOR offices/laboratory, e-library and classrooms (including seminar and conference halls), canteen and baby-friendly centre | This will ease teaching, learning and research challenges, enhance access to e-library and good learning environment, enhance teaching, learning and research by faculties and students | 220000 | Better use of facilities by students and faculties for wider visibility, and sustainability of ACE-CEFOR | Procurement
| Total |  |  | 2228000
| Operating Expenses 10% |  |  | 222800
| Grand Total |  |  | 2450800
EXCHANGE RATE: ₦411 = U.S. $1

## Procurement Plan Works
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (WORKS) FOR JANUARY - DECEMBER 2022 (12 MONTHS)
[9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
WORKS |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US $ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost in US $
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
CEFOR Building (external works landscaping, maintenance of facilities in building). Details include a mini-laboratory, a canteen and a baby-friendly centre, road safety signs, CCTV gadgets, refuse receptacles and cleaning equipment | NG/CEFOR/WKS/ST/2022/10 | 10 | Bill of Quantities | Selective Tendering¶ | 220000 | Post | Post | Plan | NA | NA | NA | 2022-03-18 | 2022-01-04 | NA | NA | Plan | 220000 | 2022-08-04 | NA | 2022-04-16 | 2022-04-23 | 2022-05-27 | 2022-06-06 | 220000
Project management (10% of project cost) |  |  |  |  | 22000
Total Cost |  |  |  |  | 242000 |  |  | Plan | [7 empty] | Plan | 220000 | [6 empty] | 220000
[8 empty] | Actual | [7 empty] | Actual
Fill gray cells only! |  | EXCHANGE RATE: ₦411 = U.S. $1
¶KEY:
| 1 | To, as much as is possible, ensure work continuation coupled with difficulty in reproducing by another vendor, and since the existing contractor did not default in the first instance but, hindered by project fund source.
| 2 | Defining the exact needs of the requirements for completing the project is also very complicated, which may pose a great challenge for open tendering.
| 3 | Generally, the proposed procurement method shall help save time and money for ACE-CEFOR

## Procurement Plan Goods
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (GOODS) FOR JANUARY - DECEMBER 2022 (12 MONTHS)
GOODS |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation |  |  |  | Link to Results
Description | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance | Final Cost (US $)
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Communication and marketing. Procure and print newsletters, CEFOR annual report, postgraduate handbook, flyers, notice board, bill board, door/office tag, and self assessment of impact, as applicable | NG/CEFOR/GDS/NS/2022/01 | I | 40000 | National Shopping* | Post | Post | Plan | NA | NA | NA | 2022-01-20 | 2022-02-03 | NA | NA | Plan | 40000 | 2022-02-10 | NA | 2022-02-17 | NA | Mar; Jun; Sept; Dec 2022 | Apr; Jul; Oct; Dec 2022 | 40000 | DLI#s 2; 3; 4; 7
Administrative charges. Procure stationery, realms of paper, toners for printers, maintenance of internet facility and other office equipment, as well as quality fiduciary and procurement processes, as applicable | NG/CEFOR/GDS/NS/2022/02 | 2 | 70000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2022-01-20 | 2022-02-03 | NA | NA | Plan | 70000 | 2022-02-10 | NA | 2022-02-17 | NA | Mar; Jun; Sept; Dec 2022 | Apr; Jul; Oct; Dec 2022 | 70000 | DLI#s 2; 3; 4; 5; 6; 7
Teaching aids (MIS/LMS equipment like, projectors, data services, internet connectivity) maintenance. Make up teaching aids and data services, maintenance, replacement, if any | NG/CEFOR/GDS/NCB/2022/03 | 3 | 150000 | National Shopping | Post | Post | Plan | NA | NA | 2022-07-02 | 2022-02-21 | 2022-04-04 | NA | NA | Plan | 150000 | 2022-11-04 | 2022-11-04 | 2022-04-18 | 2022-04-25 | 2022-05-24 | 2022-06-06 | 150000 | DLI#s 3; 4; 7
Books & journals. Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR, maintenance of laboratory furniture, if any | NG/CEFOR/GDS/NCB/2022/04 | 4 | 70000 | National Shopping | Post | Post | Plan | NA | NA | 2022-07-02 | 2022-02-21 | 2022-04-04 | NA | NA | Plan | 70000 | 2022-11-04 | 2022-11-04 | 2022-04-18 | 2022-04-25 | 2022-05-24 | 2022-06-06 | 70000 | DLI#s 3; 4; 7
200 kVA Diesel Generator with transformer and accessories. Procure fuel (diesel), servicing, repairs, maintenance, logistics for generator attendant, if any | NG/CEFOR/GDS/NS/2022/05 | 5 | 80000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2022-01-20 | 2022-02-03 | NA | NA | Plan | 80000 | 2022-02-10 | NA | 2022-02-17 | NA | Mar; Jun; Sept; Dec 2022 | Apr; Jul; Oct; Dec 2022 | 80000 | DLI#s 1; 2; 3; 4; 5; 6; 7
Project vehicles (Procure 1no Project car, 1no 30-seater bus, fuelling (petrol), servicing, repairs, maintenance, etc) | NG/CEFOR/GDS/NS/2022/06 | 6 | 200000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2022-01-20 | 2022-02-03 | NA | NA | Plan | 200000 | 2022-02-10 | NA | 2022-02-17 | NA | Mar; Jun; Sept; Dec 2022 | Apr; Jul; Oct; Dec 2022 | 200000 | DLI#s 1; 2; 3; 4; 5; 6; 7
Laboratory equipment and associated furniture, reagents, maintenance. Make up procurement, installation and maintenance of sundry laboratory equipment with associated furniture, IEC materials to support COVID-19 awareness campaign | NG/CEFOR/GDS/NCB/2022/07 | 7 | 240000 | National Shopping | Post | Post | Plan | NA | NA | 2021-07-02 | 2022-02-21 | 2022-04-04 | NA | NA | Plan | 240000 | 2022-11-04 | 2022-11-04 | 2022-04-18 | 2021-04-25 | 2021-05-24 | 2022-06-06 | 240000 | DLI#s 1; 2; 3; 4; 5; 7
Office, e-library and classroom furniture with accessories. Make up procurement, installation and maintenance of sundry office, and e-library and internet support for partner centres/departments/units in UniPort | NG/CEFOR/GDS/NCB/2022/08 | 8 | 100000 | National Shopping | Post | Post | Plan | NA | NA | 2022-07-02 | 2022-02-21 | 2022-04-04 | NA | NA | Plan | 100000 | 2022-11-04 | 2022-11-04 | 2022-04-18 | 2022-04-25 | 2022-05-24 | 2022-06-06 | 100000 | DLI#s 3; 4; 7
e-Procurement software. Procure and install facilities/furniture, e-procurement/e-accounting/e-auditting software for ACE-CEFOR Procurement/Accounting/Audit Units | NG/CEFOR/GDS/DC/2022/09 | 9 | 55000 | National Shopping | Post | Post | Plan | NA | NA | 2022-05-03 | 2022-03-19 | 2022-04-02 | NA | NA | Plan | 55000 | 2022-09-04 | 2022-04-16 | 2022-04-19 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 55000 | DLI#s 4; 6; 7
Project management (10% of project cost) |  |  | 100500
Total Cost |  |  | 1105500 |  |  |  | Plan | [7 empty] | Plan | 1005000 | [6 empty] | 1005000
[7 empty] | Actual | [7 empty] | Actual
Fill gray cells only! | EXCHANGE RATE: ₦411 = U.S. $1
KEY:
|  | * | National Shopping shall be used because, they require continuous / quarterly supplies estimated to be less than NGN ₦ 5,000,000, which is not very easy to directly quantify since the needs for maintenance often vary per time

## Procurement Plan Consultancy
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (CONSULTANCY) FOR JANUARY - DECEMBER 2022 (12 MONTHS)
For Contracts under projects approved before the May 2002 Guidelines
|  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
Description | Selection Method | Lumpsum or Time-Based | Estimated Amount in US $ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost in US $
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Development Impact. Procure consulting services for independent external evaluation of impact, as well as vigorous marketing of CEFOR’s programs to national & international target audience, regional student recruitment, publicity and outreach, scientific image, as applicable. | Single Source Selection† | Lump sum | 70000 | Post | Plan | 2022-01-18 | 2022-08-02 | NA | NA | NA | NA | Plan | 2022-10-02 | NA | NA | NA | NA | NA | NA | Plan | 2022-02-15 | 2022-02-22 | 70000 | 2022-01-03 | 2022-02-03 | 2022-10-03 | Plan | 2022-03-17 | 2022-09-13 | 2022-11-10 | 70000
Institutional Impact. Procure annual internet support services (NgREN; with e-resources and associated internet access & connectivity for UniPort). | Single Source Selection‡ | Lump sum | 100000 | Post | Plan | 2022-01-18 | 2022-08-02 | NA | NA | NA | NA | Plan | 2022-10-02 | NA | NA | NA | NA | NA | NA | Plan | 2022-02-15 | 2022-02-22 | 100000 | 2022-01-03 | 2022-02-03 | 2022-10-03 | Plan | 2022-03-17 | 2022-09-13 | 2022-11-10 | 100000
Support multi-year annual institutional membership dues and subscriptions to AAU, ACU, RUFORUM, etc | Single Source Selection‡ | Lump sum | 70000 | Post | Plan | 2022-02-07 | 2022-03-28 | NA | NA | NA | NA | Plan | 2022-03-30 | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-13 | 70000 | 2022-04-20 | 2022-04-21 | 2022-04-28 | Plan | 2022-07-05 | 2022-08-04 | 2022-09-06 | 70000
Accreditation/Gap analysis for international accreditation gap analysis, self evaluation/close-ups for Centre programmes | Single Source Selection† | Lump sum | 100000 | Post | Plan | 2022-02-07 | 2022-03-28 | NA | NA | NA | NA | Plan | 2022-03-30 | NA | NA | NA | NA | NA | NA | Plan | 2022-04-06 | 2022-04-13 | 100000 | 2022-04-20 | 2022-04-21 | 2022-04-28 | Plan | 2022-07-05 | 2022-08-04 | 2022-09-06 | 100000
Project management (10% of project cost) |  |  | 34000 | [19 empty] | 34000 | [7 empty] | 34000
Total Cost |  |  | 374000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 374000 |  |  |  | Plan |  |  |  | 374000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Fill gray cells only! | EXCHANGE RATE: ₦411 = U.S. $1
KEY:
|  | † | ACE-CEFOR has understanding with Africa Development Futures Group (a reputable international online communication, marketing and admission management solution entity) to, effectively, handle the aspect of recruiting international and regional students meeting DLI #2
|  | ‡ | It was agreed that, the ACE Project Coordinating Agency in Nigeria (National Universities Commission, NUC) was mandated to provide NgREN basic services for all the Nigerian ACEs to subscribe to the Nigerian Research and Education Network (NgREN)

## Procurement Plan Training
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (TRAINING) FOR JANUARY - DECEMBER 2022 (12 MONTHS)
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Effective Higher Education Institutions management in sub-Saharan Africa during and after COVID Pandemic for desired results | Prof. O.A. Georgewill | To enhance skill set form managing Higher Education Institutions in times of uncertainty | Inmproved leadership during and after periods of uncertainty and shrinking funding | Within and outside Nigeria | 15000
2 | 1) Understanding and applying effective business to business (B2B) marketing for successful development of a Centre of Excellence. 2) SPE International Conference on Oilfield Chemistry | Prof. Ogbonna F. Joel | To, effectively, apply blended (online and face-to-face) marketing for growing a centre of excellence | Increased awareness about ACE-CEFOR activities and regional relevance of Centre training and research programmes | Within and outside Nigeria | 18000
3 | 1) Project Management during and after COVID 2) SPE International Conference on Oilfield Chemistry | Prof. Onyewuchi Akaranta | 1) To enhance capacity to cope with the shocks introduced by the COVID Pandemic and effective project management skills to improve performance. 2) To showcase recent findings from CEFOR innovative research and share knowledge with other experrts | Imoroved ACE-CEFOR visibility and service delivery for regional impact in Higher Education Institutions of Africa | Within and outside Nigeria | 15000
4 | 1) Understanding and applying effective business to business (B2B) marketing for successful development of a Centre of Excellence. 2) Successful planning, organising and delegation in a centre of excellence during and after COVID-19 Pandemic | Prof. Ikechukwu O. Agbagwa | 1) To enhance capacity to cope with the shocks introduced by the COVID Pandemic and effective project management skills to improve performance. 2) To enhance planning skills, manage resources and improve work behaviours | Imoroved work performance and service delivery for impact in Higher Education Institutions | Within and outside Nigeria | 15000
5 | 1) Rethining the importance of procurement post-COVID Pandemic. 2) Level 3 training in advanced practices in public procurement towards Advanced Certificate in Public Procurement organised by UNDP. 3) Level 4 training in public procurement towards a Diploma in Strategic Public Procurement organised by UNDP | Prof. Ibisime Etela | To manage with new ways of working in procurement and improve partipants capacity towardds becoming global certfied procurement specialists | Improved procurement process for enhanced project delivery during and after COVID Pandemic and other possible future such situations | Within and outside Nigeria | 15000
6 | 1) Training on emerging trends in Financial Accounting and Forensic Practices. 2) Financial Accounting Responsibility | Dr. Ben Woko | To deepen practical orientation in Accounting and prepare participants with the requisite training for the 21st Century Financial Accounts preparation and reporting | It will sharpen the skills of Accounting Practitioners and enhance their capacity to develop responsive Financial Accounts preparation and Auditing | Within and outside Nigeria | 12000
7 | 1) Training on emerging trends in Financial Accounting and Forensic Practices. 2) Financial Accounting Responsibility | Dr. Benson P. Timah | To deepen practical orientation in Accounting and prepare participants with the requisite training for the 21st Century Financial Accounts preparation and reporting | It will sharpen the skills of Accounting Practitioners and enhance their capacity to develop responsive Financial Accounts preparation and Auditing | Within and outside Nigeria | 12000
8 | Monitoring and evaluation (M&E) workshop for senior executives, government officials, development managers, and civil society that provides learning from past experiences, thereby improving service delivery, planning and allocating resources, and evaluating results as part of accountability to key stakeholders | Mr. Uduma Ikpa | 1) To improve the operation and management of the ACE-CEFOR M&E function. 2) To improve the effectiveness of the ACE-CEFOR M&E process to help assess programme impacts | Improved M&E skills for high project impact during and after COVID Pandemic | Within and outside Nigeria | 12000
9 | 1) Communication, coordination and leadership for, effectively, communicating with stakeholders during and after COVID-19 Pandemic. 2) Developing ansd implementing strategic marketing plan | Communication Officer/Secretary to Centre Leader | To enhance leadership and supervisory skills for supporting ACE-CEFOR activities | Imcreased reputtation of ACE-CEFOR for doing business | Within and outside Nigeria | 12000
10 | 1) Managing projects for environment, social and management plan compliance 2) Effective management of university-industry linkage for successful public-private partnership during and after COVID-19 Pandemic | Safeguard Officer (Dr. Victor Joseph Aimikhe) | To enhance capacity for managing environmental and social issues from project implementation | Improved environmental and social impacts of prject | Within and outside Nigeria | 12000
11 | Training and certification of faculty members and students by the National Registry of Environmental Professionals (NREP), USA | Identified faculty members and students | To increase employability of participants | Trained and certified candidates become very marketable and employable upon graduation | ACE-CEFOR | 70000
12 | Organise workshops and seminars in: 1) Effective laboratory management; 2) Principles and procedures for securing ISO Certification for laboratories in Higher Education Institutions; 3) HSE Training; 4) Skills and techniques for developing fundable grants and managing donor funded projects in Higher Education Institutions; 5) Capacity building for university-industry partnership towards efficient commercialisation of positive research results; 6) Developing a high performance and excellent team | To be identified as nominated by partnering departments and organisations per session | To contribute towards social and institutional impact of the ACE-CEFOR project | Contribute to the achievement of desired ACE-CEFOR development goals and ensure early warning and strategies for preventing failures | ACE-CEFOR | 12000
13 | Students and faculty members support through scholarship, research, publications, supervision, internship, invite visiting scholars, conferences, seminars and workshops | Students and faculty members | To attend conferences/seminars/workshops; communicate research findings; students/faculty members development, host visiting scholars, carry out research for innovation and publicity | Increased capabilities of faculty members and students in the sub-region to adopt global best practices in research and training in Petroleum and related disciplines. and quality postgraduate education, knowledge transfer and internship programmes | To be determined | 250000
14 | Attend and participate at ACE approved meetings | All ACE-CEFOR Steering Committee members | To make presentations for promoting the visibility of ACE-CEFOR through progress report and highlighting performance | Better informed staff for high staff productivity and greater project impact | To be determined | 143000
15 | Sustain recognition as Regional Centre of Expertise (RCE) | Stakeholders from host communities for implementing sustainable development projects | Promote science education at all levels to enhance attainment of the UN Post-2015 Sustainable Development Goals (SDGs), better responses to socio-economic needs, and greener production processes in the petroleum and environmental studies sectors | Increased knowledge on new thinking in SDGs implementation for adoption of green technologies and chemicals for eco-friendly industry operations | To be determined | 50000
16 | Project management (10% of project cost) |  |  |  |  | 66300
[5 empty] | TOTAL | 729300
EXCHANGE RATE: ₦411 = U.S. $1

## Disbursement Plan
COUNTRY: NIGERIA
PROJECT: WORLD BANK AFRICA CENTRE OF EXCELLENCE PROJECT
CENTRE: AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
CREDIT NO: GRANT ID# - 60029544
DISBURSEMENT PLAN (JANUARY - DECEMBER, 2022)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 | Teaching Aids; Lab. Equip. |  |  | 15000 | 82500 |  | 15000 | 82500 |  | 15000 | 82500 |  | 15000 | 82500 |  | 390000
2 | Books & Journals; Office e-Library; e-Procurement softwares |  |  | 65000 | 20000 |  | 60000 | 20000 |  | 60000 | 20000 |  | 60000 | 20000 |  | 325000
3 | 200KVA Gen.; Project Vehicles; CEFOR Building |  | MONTHS FEB: 80000; MONTHS MAR: 100000; MONTHS APR: 140000; MONTHS MAY: 65000; MONTHS JUL: 25000; MONTHS SEP: 65000; MONTHS NOV: 25000; MONTHS TOTAL: 500000
TRAINING
1 | NREP, ACE Meeting, Stort Courses, Students/Faculties |  |  | 37500 | 71500 | 132500 | 37500 | 62500 |  | 62500 | 37500 |  | 71500 | 37500 | 62500 | 613000
CONSULTANCIES
1 | Accreditation/Gap Analysis |  | MONTHS APR: 100000; MONTHS TOTAL: 100000
2 | Negotiate/Sign |  | MONTHS MAR: 70000; MONTHS TOTAL: 70000
OPERATING COST
1 | Sustain Recognition; Administrative Charges |  |  | 6000 | 6000 | 30000 | 6000 | 6000 | 6000 | 6000 | 6000 | 30000 | 6000 | 6000 | 6000 | 120000
2 | Communication; Vigorous Online Marketing |  |  |  | 10000 | 15000 | 15000 | 10000 |  | 10000 | 20000 |  | 10000 | 20000 |  | 110000
3 | Project Management (Operating Expenses) |  |  | 12350 | 27000 | 34750 | 37350 | 24600 | 600 | 17850 | 16600 | 9500 | 16250 | 19100 | 6850 | 222800
| TOTAL |  |  | 135850 | 297000 | 382250 | 410850 | 270600 | 6600 | 196350 | 182600 | 104500 | 178750 | 210100 | 75350 | 2450800
EXCHANGE RATE: ₦411 = U.S. $1