ACE for Development Impact (ACE Impact)

2023 Annual Workplan Narrative

(to be submitted along with the attached detailed work plan and budget)

| Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR) |
| --- | --- |
| Institution | University of Port Harcourt |
| Country | Nigeria |
| Center Leader | Professor Ogbonna Friday Joel |
| Annual Workplan | January 01-December 31, 2023 |

Narrative

- Center Highlights in 2022 (maximum of 3 Highlights, maximum 100 words each) In a concise, descriptive statement suitable for public understanding, provide up to three Highlights from the Center accomplishments in the past year.  You may attach:  weblinks; press releases; photographs.

- The Centre received national accreditation by the National Universities Commission (NUC) for 16 of its programmes. The accreditation will last for 5 years.

- The ACE-CEFOR conducted online interviews and admitted the 6th Batch of 38 PhD students billed to graduate in 2025. Hybrid lectures (blend of online and physical) are ongoing through our Learning Management System (LMS) Platform.

- Participated in the 2nd and 3rd West Africa Centers of Excellence on Energy Network (WACEENET) Regional Symposiums, respectively, in May and October 2022. The 2nd Symposium was on Clean Energy, while the 3rd Symposium was on Sustainable Energy Development. Participants include faculty members and students from the five ACE Impact member centers comprising one each from Ghana (1. Regional Centre of Excellence on Energy and Sustainability, RCEES) and Togo (2. Centre d’Excellence Régional pour la Maîtrise de l’Electricité, CERME), and three from Nigeria (3. Africa Centre of Excellence for Sustainable Power and Energy Development, ACE-SPED; 4. Africa Centre of Excellence for Future Energy Systems, ACE-FUELS, and 5. Africa Centre of Excellence for Oilfield Chemicals Research, ACE-CEFOR).

- Key Center Achievements in 2022 (Maximum 500 words) Describe the Key Accomplishments of the Center in the preceding Calendar Year.  Focus on: Teaching, Research, Center-level Operations.  In addition, comment on how the Accomplishments align with the ACE Impact Project Disbursement Linked Indicators (DLIs) and the Center Implementation Plan.

- Generally, the Centre has achieved 56% of total expected earnings.

- In April 2022, the Centre secured five-year Full National Accreditation by the National Universities Commission (NUC) for 16 programmes, namely:

  - M.Sc. in Petroleum Engineering & Project Development; Petroleum Geosciences; Gas, Refining & Petrochemical Engineering;. Occupational Health & Safety; Environmental Technology & Management; Natural Resources & Environmental Management; and

  - Ph.D. in Natural Resources & Environmental Management; Geology; Chemistry; Industrial Chemistry; Occupational Health & Safety; Environmental Technology & Management; Chemical Engineering; Petroleum & Gas Engineering; Microbiology; and Biotechnology.

- In August 2022, the 6th Batch of 38 PhD students were admitted, compared to the 25 in 2021, 46 in 2020 and 57 in 2019. Cumulative to date, is 166 PhDs. The Centre achieved 100% earnings in 2021. (DLI 3.1)

- A total of 95 MSc students were admitted, compared to 80 in 2021, 149 in 2020 and 114 in 2019. Cumulative to date, is 438 MSc students, giving 33% earnings. (DLI 3.2)

- Organized short courses for 183 persons (with 6 regional), compared to 338 in 2021 (with 70 regional) and 59 in 2019, (with 54 regional). Short courses were not organized in 2020 due to COVID-19 lockdowns. Cumulative to date, is 580 short course participants trained. The Centre achieved 100% earnings in 2021. (DLI 3.3)

- A total of 36 papers were published in high quality journals, compared to 36 in 2021, 38 in 2020 and 67 in 2019. Cumulative to date, is 157 papers giving 50% earnings from publishing research findings in high quality journals. (DLI 4.2)

- Externally generated revenue of $688,962.04  was earned, with $709,300.99 earned in 2021, $456,174.14 earned in 2020, while EGR in 2019 was zero. Cumulative to date, is $1,854,437.17. The Centre achieved 100% earnings in 2021. (DLI 5.1)

- In May and October 2022, ACE-CEFOR, took part in the 2nd and 3rd West Africa Centers of Excellence on Energy Network (WACEENET) Regional Symposiums. WACEENET a group of Energy and Power Thematic ACE Impact Centers, is made up of Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED), Nigeria; Regional Centre of Excellence on Energy and Sustainability (RCEES), Ghana; Africa Centre of Excellence for Future Energy Systems (ACE-FUELS), Nigeria; Centre d’Excellence Régional pour la Maîtrise de l’Electricité (CERME), Togo; and Africa Centre of Excellence for Oilfield Chemicals Research (ACE-CEFOR), Nigeria. (DLI 5.1)

- In November 2022, ACE-CEFOR PhD student, Ms. Chinonye Medline Maduka, received the 2022 ACE Impact Student Innovation Research Award (SIRA), during the 8th ACE Impact Regional Workshop in Banjul, The Gambia, for her research work on, “The use of organics to formulate brake fluid”.

- Status/Progress on Implementation (Maximum 250 words) Describe in what ways, if any, the Center is ahead of schedule with respect to the Implementation Plan.

- In October 2021, the Center received confirmation from the Association of African Universities (AAU) that, it had achieved 100% status for earnings of the funds due it for DLI 3.3 (New Professional Short Course Students), with an outstanding balance of $5,061 due the Center. To date, additional Short Courses have been organised..

- Still in October 2021, ACE-CEFOR also received confirmation from the AAU that, it had achieved 100% status for DLI 5.1 (External Revenue). Similarly, the Centre has  generated more externally generated revenue to date.

- The 38 new PhD students admitted in 2022 was above the 12 new PhD students approved as target for 2022. The Center has since exceeded the 56 PhDs targeted for the five-year ACE-Impact Project by 110 PhD students having already admitted 166 PhD students since project effectiveness. (DLI 3.1)

- New MSc students as at 2022 is 95 (compared to the targeted 15 new MSc for 2022 and 80 for the five-year duration of ACE-Impact. (DLI 3.2)

- New international publications for 2022 were 36, while in 2021 publications were 36, compared to the targeted 10 publications for each year. Total publications for both years is 72 (which is 22 above the targeted new international publications of 50 for the five-year duration of ACE-Impact. (DLI 4.2)

- Plan for Acceleration (Maximum 500 words) Describe in what ways, if any, the Center is behind schedule with respect to the Implementation Plan.  How will the Center adjust to achieve the anticipated project deliverables by the conclusion of ACE Impact?

| # Table 1: Center targets behind schedule with reasons and proposed mitigation plan |  |  |
| --- | --- | --- |
| # DLI Behind Schedule | # Reason | # Mitigation Plan |
| # DLI 4.3 # (Infrastructure Improvement) | # Delayed approval of ESMP | # The Centre Safeguard and Environment Officer is following up with the WB ESMP Expert to address this issue soonest |
| # DLI 4.3 # (Infrastructure Improvement) | # Inability to meet increasing demands for laboratory facilities | # Expedite action on the approval process of the ESMP to enable the Centre initiate and complete efforts aimed at expanding the existing laboratory facilities for use |
| # DLI 7.3 # (Institutional Impact) | # Non-release of funds | # Institutional Impact now being implemented since funds have been released |

- Key changes to approved IP, including Covid-19 Related Activities (Maximum 500 words) Describe in what ways, if any, the Center proposes changes to its approved Implementation Plan.  Focus on the reasons for the proposed changes, any impact on the proposed activities, and how the proposed changes will affect the anticipated projects deliverables.

- Although the Centre’s activities are majorly on course, the area of major change in the Implementation Plan envisaged is in the incorporation of the new targets occasioned by the additional expected earnings following the allocation of additional funds to the Centre having achieved 56% of its approved overall project targets based on the mid-term project review report. However, should there be need for such changes, the Centre shall follow the required due diligence and seek a “No Objection” from the World Bank through the AAU, Accra, Ghana and the NUC, Abuja, Nigeria.

- Also, due to increasing demands for meeting the expectations of our students, the Centre intends to expand the existing laboratory facilities by acquiring new laboratory spaces and equipment to carter for the laboratory needs of our students, especially the regional students, to enable them continue to complete their researches in record time.