## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
General Work Plan
| Table 1-1 | General Work Plan - Table 1-1
Procurement Plan Works
| Table 1 | Procurement Plan Works
Procurement Plan Goods
| Table 1 | Procurement Plan Goods
Procurement Plan Consultancy
| Table 1 | Procurement Plan Consultancy
Procurement Plan Training
| Table 1 | Procurement Plan Training
Disbursement Plan
| Table 1 | Disbursement Plan

## General Work Plan - Table 1-1
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: WORK PLAN FOR JANUARY - DECEMBER 2023 (12 MONTHS)
WORK PLAN (JANUARY - DECEMBER 2023)
Year 2023
Activity No | ACTIVITY |  | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT | January - December 2023
[7 empty] | J | F | M | A | M | J | J | A | S | O | N | D
[7 empty] | A | E | A | P | A | U | U | U | E | C | O | E
[7 empty] | N | B | R | R | Y | N | L | G | P | T | V | C
GOODS
1 | Communication and marketing | Newsletters/advertisement | This is necessary for centre publicity, public awareness and stakeholders information, engagement, visibility and marketing | 35000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa with wider visibility, acceptance and patronage within and outside West and Central Africa | Communication / M&E / Procurement Officers
2 | Teaching aids (MIS/LMS equipment like, projectors, data services, internet connectivity) maintenance | Make up teaching aids and data services, maintenance, replacement, if any | This will enable the Centre provide efficient learning environment, facilitate efficient course delivery | 150000 | Improved preference for teaching, learning and research for lifelong learning by students and faculty | Procurement
3 | Books & journals. Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR/partner units, library catalogue software/renewals | Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR/partner units, maintenance of laboratory furniture | This will ease learning challenges, enhance access to print literature, promote patenting in university, etc, enhance teaching, learning and research by faculties and students | 70000 | Preference for use of ACE-CEFOR library by students and faculty for increased scholarship, innovative research, publication and patenting | Procurement
4 | 150 kVA Diesel Generator with transformer and accessories/backup power supply/Inverter batteries/electricity maintenance | Buy soundproof gen set; transformer; fuelling (diesel), servicing, repairs, maintenance, install and maintain backup power, maintain electrical appliances, logistics for generator attendant, if any | Back-up power failure to enhance teaching, learning and research by faculties and students, enhance teaching, learning and research environment | 95000 | Increased motivation of staff and faculty for improved staff and faculty productivity | Procurement
5 | Project vehicles (fuelling (petrol), servicing, repairs, maintenance, etc) | Fuelling (petrol), servicing, repairs, maintenance of project vehicles | Provides transportation logistics for centre leader and other steering committee members as well as faculties and students on field tours and visits | 20000 | Improved job satisfaction, enhanced capacity to secure accreditation for increased productivity | Procurement
6 | Laboratory equipment and associated furniture, reagents, maintenance/lab staff training | Make up procurement, installation and maintenance of sundry laboratory equipment with associated furniture | This will lead to proper handling of procured equipment, repair laboratory space in readiness for receiving equipment, health training materials | 230000 | Improved preference for teaching, learning and research for lifelong learning by students and faculties, better informed staff and stakeholders for safety and wellness | Procurement
7 | Office, e-library and NgREN internet hardware support for CEFOR/partner centres/departments/units in UniPort | Installation/support annual upgrade/extension of facilities like NgREN, mHealth, etc | This is necessary to prepare offices, e-library and classrooms for better working environment, make CEFOR building fully functional for enhanced service delivery | 250000 | Improved preference for teaching, learning and research for lifelong learning by students and faculties | Procurement
8 | e-Procurement software. Procure and install facilities/furniture, e-procurement/e-accounting/e-auditting software for ACE-CEFOR Procurement/Accounting/Audit Units | Procure and install facilities / furniture, e-procurement software/E-Auditing, M/E Software, Upgrade of University of Port Harcourt ERP Software_ and project management software/resource planning | This shall ensure increased timely and transparent institutional procurement/Audit/Monitoring and Evaluation and overall Centre's and University process with improved value for money | 150000 | Improved e-procurement knowledge by procurement staff for effective and efficient institutional Procurement Unit | Procurement
9 | Administrative charges (bank transactions; bills, stationery, realms of paper, toners for printers, maintenance of internet facility and other office equipment, as well as quality fiduciary and procurement processes, as applicable | Day-to-day running of the Centre and coordination of all activities | This will ensure Holistic and strategic management of the Centre, ensure coordinated project implementation and delivery, support maintenance logistics for ACE-CEFOR, etc | 80000 | Increased awareness about institutional benefits of improved financial and procurement processes for more public and private partners working with ACE-CEFOR and UniPort | Centre Leader
|  |  | SUBTOTALS (GOODS) | 1080000
WORKS
10 | CEFOR Building (external works landscaping, maintenance of facilities in building). Details: extension of mini-laboratory, expansion of gen house, relocate gen house of Biotechnology Centre for safety at baby-friendly room | Complete building to house extension of CEFOR offices/laboratory, power supplies | This will ease teaching, learning and research challenges, enhance access to e-library and good learning environment, enhance teaching, learning and research by faculties and students | 250000 | Better use of facilities by students and faculties for wider visibility, and sustainability of ACE-CEFOR | Procurement
|  |  | SUBTOTALS (WORKS) | 250000
CONSULTANCY SERVICES
11 | Strategic Marketing. Vigorious online marketing and campaigns within and outside region, Develop research/patents/grants portal | Embark on / sustain exploratory and consolidation trips to institutions of interest and online contacts within and outside Nigeria | Increased publicity and patronage to attain greater regional relevance for the ACE-CEFOR project, Solicit patronage from potential partners and establish new partnerships | 50000 | More prospective partners and clients aware of ACE-CEFOR products and services for Centre sustainability | Centre Leader
12 | Institutional Impact: NgReN Subscriptions for Internet service/ journals, distribution to centres/departments/units in UniPort | Annual subscriptions to NgReN, and effective distribution in the University | This is necessary to prepare offices, e-library and classrooms for better working environment, subscribe to effective tier 1 internet service and journals for research purposes | 100000 | Improved preference for teaching, learning and research for lifelong learning by students and faculties | Procurement
13 | Partnerships and Annual Subscriptions to institutional associations and networks. Negotiate/sign memoranda, and commitment to partners, renewal of AAU, ACU, RUFORUM, etc and Uniport health portal | Follow up with identified partners to firm up partnership, support multi-year annual institutional membership dues to AAU, ACU, RUFORUM, etc and Uniport health portal functionality | Entering into memorandum of understanding will strengthen project, increase regional presence and good collaboration, cover costs for travels, annual subscriptions for regional partnership to enhance regional students enrolment | 100000 | Increased preference for ACE-CEFOR and sustainability of ACE-CEFOR | Centre Leader / Deputy Centre Leader
14 | Accreditation/Gap analysis for international accreditation gap analysis, self evaluation/close-ups for Centre programmes | International accreditation gap analysis, self evaluation/close-ups | This will create easy platform for collaboration, regional students enrolment and enhance visibility and marketability | 20000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa wtih, globally, recognised postgraduate programmes and global clients base | Centre Leader / Deputy Centre Leader
|  |  | SUBTOTALS (CONSULTANCY) | 270000
NON-CONSULTING SERVICES (TRAINING)
15 | Students and interns support through scholarship, research, publications, supervision, internship,, conferences, seminars and workshops | Scholarship, research, publications, supervision, internship, invite visiting scholars, conferences, seminars and workshops | Attend conferences/seminars/workshops; Communicate research findings; Students/Faculty development, host visiting scholars, Research and innovation and publicity | 195000 | Increased capabilities of faculties and students in the sub-region to adopt global best practices in research and training in Petroleum and related disciplines. and quality postgraduate education, knowledge transfer and internship programmes | Centre Leader
16 | Training other faculty members, other than steering committee members, and visiting scholars support for training, research, publications, supervision, internship, conferences, seminars and workshops | Other faculty members and visiting scholars | To attend conferences/seminars/workshops; communicate research findings; faculty members development, host visiting scholars, carry out research for innovation and publicity | 40655.39 | To attend conferences/seminars/workshops; communicate research findings; faculty members development, host visiting scholars, carry out research for innovation and publicity
17 | National Registry of Environmental Professionals (NREP), USA training and certification for faculty members and students | Training and certification by the National Registry of Environmental Professionals (NREP), USA | Training and certification by NREP shall make the certified candidates very marketable and employable upon graduation; secure NREP certification for our students and faculties for improved employability | 75000 | Strengthened capacity as a training hub for the Oil and Gas industry workforce in Africa and more protected environments and better environmental consciousness among industry players | Centre Leader
18 | Sustain recognition as Regional Centre of Expertise (RCE) | Hold stakeholders meetings; develop and submit concepts/proposals for funding; embark on sustainable development projects | Promotion of science education at all levels will enhance attainment of the UN Post-2015 Sustainable Development Goals (SDGs), better responses to socio-economic needs, and greener production processes in the petroleum and environmental studies sectors | 40000 | Increased knowledge on new thinking in SDGs implementation for adoption of green technologies and chemicals for eco-friendly industry operations | Procurement
19 | Attend ACE meetings and other relevant professional trainings | Participate at ACE approved meetings and other trainings to contribute to delivery | Visibility and progress report, Highlight performance and make presentations | 274000 | Better informed staff for high staff productivity and greater project reach out | Centre Leader
20 | Organise and attend short courses by steering committee members and other stakeholders | Hold and attend short courses | Improved service delivery and performance, enhance capacity of steering committee members, carry out consultancy services for the oil and gas industry | 50000 | Improved staff capacity to organise trainings and deliver modules for wider ACE-CEFOR/UniPort visibility, acceptance and patronage within and outside West and Central Africa | Centre Leader
21 | Training support for CEFOR staff who provide critical administrative and auxilliary services like laboratory technicians, drivers, administrative staff, etc | Administrative and auxilliary CEFOR staff | To create a critical mass of personnel for sustaining the gains from the CEFOR imoacts | 15000 | To enhance overall staff productivity and project impact through human capital development across all levels
|  |  | SUBTOTALS (NON-CONSULTING) | 689655.39
| Total |  |  | 2289655.39
22 | Operating Expenses 10% | Project management | Project efficiency | 114482.7695 | Improved project impact
| Grand Total |  |  | 2404138.1595
|  | EXCHANGE RATE: ₦445 = U.S. $1 |  | 2404138.16 | Available Funds Balance

## Procurement Plan Works
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (WORKS) FOR JANUARY - DECEMBER 2023 (12 MONTHS)
[9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
WORKS |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US $ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost in US $
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
CEFOR Building (external works landscaping, maintenance of facilities in building). Details: extension of mini-laboratory, expansion of gen house, relocate gen house of Biotechnology Centre for safety at baby-friendly room | NG/CEFOR/WKS/ST/2023/10 | 10 | Bill of Quantities | Selective Tendering¶ | 250000 | Post | Post | Plan | NA | NA | NA | 2023-03-18 | 2023-01-04 | NA | NA | Plan | 250000 | 2023-08-04 | NA | 2023-04-16 | 2023-04-23 | 2023-05-27 | 2023-06-06 | 250000
Project management (5% of project cost) |  |  |  |  | 12500 | [11 empty] | 12500 | [6 empty] | 12500
Total Cost |  |  |  |  | 262500 |  |  | Plan | [7 empty] | Plan | 262500 | [6 empty] | 262500
[8 empty] | Actual | [7 empty] | Actual
Fill gray cells only! |  | EXCHANGE RATE: ₦445 = U.S. $1
¶KEY:
| 1 | To, as much as is possible, ensure work continuation coupled with difficulty in reproducing by another vendor, and since the existing contractor did not default in the first instance but, hindered by project fund source.
| 2 | Defining the exact needs of the requirements for completing the project is also very complicated, which may pose a great challenge for open tendering.
| 3 | Generally, the proposed procurement method shall help save time and money for ACE-CEFOR

## Procurement Plan Goods
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (GOODS) FOR JANUARY - DECEMBER 2023 (12 MONTHS)
GOODS |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation |  |  |  | Link to Results
Description | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance | Final Cost (US $)
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Communication and marketing. Procure and print newsletters, CEFOR annual report, postgraduate handbook, flyers, notice board, bill board, door/office tag, and self assessment of impact, as applicable | NG/CEFOR/GDS/NS/2023/01 | I | 35000 | National Shopping* | Post | Post | Plan | NA | NA | NA | 2023-01-20 | 2023-02-03 | NA | NA | Plan | 35000 | 2023-02-10 | NA | 2023-02-17 | NA | Mar; Jun; Sept; Dec 2023 | Apr; Jul; Oct; Dec 2023 | 35000 | DLI#s 2; 3; 4; 7
Office Consumables (bills, stationery, realms of paper, toners for printers, maintenance of internet facility and other office equipment, as applicable | NG/CEFOR/GDS/NS/2023/02 | 2 | 40000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2023-01-20 | 2023-02-03 | NA | NA | Plan | 40000 | 2023-02-10 | NA | 2023-02-17 | NA | Mar; Jun; Sept; Dec 2023 | Apr; Jul; Oct; Dec 2023 | 40000 | DLI#s 2; 3; 4; 5; 6; 7
Teaching aids (MIS/LMS equipment like, projectors, data services, internet connectivity) maintenance | NG/CEFOR/GDS/NCB/2023/03 | 3 | 150000 | National Shopping | Post | Post | Plan | NA | NA | 2023-07-02 | 2023-02-21 | 2023-04-04 | NA | NA | Plan | 150000 | 2023-11-04 | 2023-11-04 | 2023-04-18 | 2023-04-25 | 2023-05-24 | 2023-06-06 | 150000 | DLI#s 3; 4; 7
Books & journals. Procure books and journals with subscriptions relevant for graduate studies at ACE-CEFOR/partner units, library catalogue software/renewals | NG/CEFOR/GDS/NCB/2023/04 | 4 | 70000 | National Shopping | Post | Post | Plan | NA | NA | 2023-07-02 | 2023-02-21 | 2023-04-04 | NA | NA | Plan | 70000 | 2023-04-11 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-24 | 2023-06-06 | 70000 | DLI#s 3; 4; 7
150 kVA Diesel Generator with transformer and accessories/backup power supply/Inverter batteries/electricity maintenance | NG/CEFOR/GDS/NS/2023/05 | 5 | 95000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2023-01-20 | 2023-02-03 | NA | NA | Plan | 95000 | 2023-02-10 | NA | 2023-02-17 | NA | Mar; Jun; Sept; Dec 2023 | Apr; Jul; Oct; Dec 2023 | 95000 | DLI#s 1; 2; 3; 4; 5; 6; 7
Project vehicles (fuelling (petrol), servicing, repairs, maintenance, etc) | NG/CEFOR/GDS/NS/2023/06 | 6 | 20000 | National Shopping | Post | Post | Plan | NA | NA | NA | 2023-01-20 | 2023-02-03 | NA | NA | Plan | 20000 | 2023-02-10 | NA | 2023-02-17 | NA | Mar; Jun; Sept; Dec 2023 | Apr; Jul; Oct; Dec 2023 | 20000 | DLI#s 1; 2; 3; 4; 5; 6; 7
Laboratory equipment and associated furniture, reagents, maintenance/lab staff training | NG/CEFOR/GDS/NCB/2023/07 | 7 | 230000 | National Shopping | Post | Post | Plan | NA | NA | 2021-07-02 | 2023-02-21 | 2023-04-04 | NA | NA | Plan | 230000 | 2023-04-11 | 2023-04-11 | 2023-04-18 | 2021-04-25 | 2021-05-24 | 2023-06-06 | 230000 | DLI#s 1; 2; 3; 4; 5; 7
Office, e-library and NgREN internet hardware support for CEFOR/partner centres/departments/units in UniPort | NG/CEFOR/GDS/NCB/2023/08 | 8 | 250000 | National Shopping | Post | Post | Plan | NA | NA | 2023-02-07 | 2023-02-21 | 2023-04-04 | NA | NA | Plan | 250000 | 2023-04-11 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-24 | 2023-06-06 | 250000 | DLI#s 3; 4; 7
e-Procurement software. Procure and install facilities/furniture, e-procurement/e-accounting/e-auditting software for ACE-CEFOR Procurement/Accounting/Audit Units | NG/CEFOR/GDS/DC/2023/09 | 9 | 150000 | National Shopping | Post | Post | Plan | NA | NA | 2023-03-05 | 2023-03-19 | 2023-04-02 | NA | NA | Plan | 150000 | 2023-04-09 | 2023-04-16 | 2023-04-19 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 150000 | DLI#s 4; 6; 7
Project management (5% of project cost) |  |  | 52000 | [12 empty] | 52000 | [6 empty] | 52000
Total Cost |  |  | 1092000 |  |  |  | Plan | [7 empty] | Plan | 1092000 | [6 empty] | 1092000
[7 empty] | Actual | [7 empty] | Actual
Fill gray cells only! | EXCHANGE RATE: ₦445 = U.S. $1
KEY:
|  | * | National Shopping shall be used because, they require continuous / quarterly supplies estimated to be less than NGN ₦ 5,000,000, which is not very easy to directly quantify since the needs for maintenance often vary per time

## Procurement Plan Consultancy
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (CONSULTANCY) FOR JANUARY - DECEMBER 2023 (12 MONTHS)
For Contracts under projects approved before the May 2002 Guidelines
|  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
Description | Selection Method | Lumpsum or Time-Based | Estimated Amount in US $ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost in US $
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Strategic Marketing. Vigorious online marketing and campaigns within and outside region, Develop research/patents/grants portal | Single Source Selection† | Lump sum | 50000 | Post | Plan | 2023-01-18 | 2023-02-08 | NA | NA | NA | NA | Plan | 2023-02-10 | NA | NA | NA | NA | NA | NA | Plan | 2023-02-15 | 2023-02-22 | 50000 | 2023-03-01 | 2023-03-02 | 2023-03-10 | Plan | 2023-03-17 | 2023-09-13 | 2023-10-11 | 50000
Institutional Impact: NgReN Subscriptions for Internet service/ journals, distribution to centres/departments/units in UniPort | Single Source Selection | Lump sum | 100000 | Post | Plan | 2023-01-18 | 2023-02-08 | NA | NA | NA | NA | Plan | 2023-02-10 | NA | NA | NA | NA | NA | NA | Plan | 2023-02-15 | 2023-02-22 | 100000 | 2023-03-01 | 2023-03-02 | 2023-03-10 | Plan | 2023-03-17 | 2023-09-13 | 2023-10-11 | 100000
Partnerships and Annual Subscriptions to institutional associations and networks. Negotiate/sign memoranda, and commitment to partners, renewal of AAU, ACU, RUFORUM, etc and Uniport health portal | Single Source Selection | Lump sum | 100000 | Post | Plan | 2023-02-07 | 2023-03-28 | NA | NA | NA | NA | Plan | 2023-03-30 | NA | NA | NA | NA | NA | NA | Plan | 2023-04-06 | 2023-04-13 | 100000 | 2023-04-20 | 2023-04-21 | 2023-04-28 | Plan | 2023-07-05 | 2023-08-04 | 2023-09-06 | 100000
Accreditation/Gap analysis for international accreditation gap analysis, self evaluation/close-ups for Centre programmes | Single Source Selection | Lump sum | 20000 | Post | Plan | 2023-02-07 | 2023-03-28 | NA | NA | NA | NA | Plan | 2023-03-30 | NA | NA | NA | NA | NA | NA | Plan | 2023-04-06 | 2023-04-13 | 20000 | 2023-04-20 | 2023-04-21 | 2023-04-28 | Plan | 2023-07-05 | 2023-08-04 | 2023-09-06 | 20000
Project management (5% of project cost) |  |  | 13500 | [19 empty] | 13500 | [7 empty] | 13500
Total Cost |  |  | 283500 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 283500 |  |  |  | Plan |  |  |  | 283500
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Fill gray cells only! | EXCHANGE RATE: ₦445 = U.S. $1
KEY:
|  | † | Extend working with existing vendors that set up the platforms and to enhance ease of upgrading and maintennace for final inegration into UniPort institutional platforms

## Procurement Plan Training
Country: NIGERIA
Loan No: Grant ID#: 60029544
Name of Institution: UNIVERSITY OF PORT HARCOURT
Organisation: WORLD BANK AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
Project/Programme: PROCUREMENT PLAN (TRAINING) FOR JANUARY - DECEMBER 2023 (12 MONTHS)
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Effective Higher Education Institutions management in sub-Saharan Africa during and after COVID Pandemic for desired results | Prof. O.A. Georgewill (Chairman and Vice Chancellor) | To enhance skill set form managing Higher Education Institutions in times of uncertainty | Inmproved leadership during and after periods of uncertainty and shrinking funding | Within and outside Nigeria | 10000
2 | 1) Understanding and applying effective business to business (B2B) marketing for successful development of a Centre of Excellence. 2) SPE International Conference on Oilfield Chemistry | Prof. Ogbonna F. Joel (Centre Leader) | To, effectively, apply blended (online and face-to-face) marketing for growing a centre of excellence | Increased awareness about ACE-CEFOR activities and regional relevance of Centre training and research programmes | Within and outside Nigeria | 10000
3 | 1) Project Management for post-COVID-19 performance of Centres of Excellence 2) SPE International Conference on Oilfield Chemistry | To be identified (DVC / ACE Project Coordinator) | 1) To enhance capacity to cope with the shocks introduced by the COVID Pandemic and effective project management skills to improve performance. 2) To showcase recent findings from CEFOR innovative research and share knowledge with other experrts | Imoroved ACE-CEFOR visibility and service delivery for regional impact in Higher Education Institutions of Africa | Within and outside Nigeria | 8000
4 | 1) Understanding and applying effective business to business (B2B) marketing for successful development of a Centre of Excellence. 2) Successful planning, organising and delegation in a centre of excellence during and after COVID-19 Pandemic | Prof. Ikechukwu O. Agbagwa (Deputy Centre Leader) | 1) To enhance capacity to cope with the shocks introduced by the COVID Pandemic and effective project management skills to improve performance. 2) To enhance planning skills, manage resources and improve work behaviours | Imoroved work performance and service delivery for impact in Higher Education Institutions | Within and outside Nigeria | 8000
5 | 1) Project management for effective and sustainable procurement post-COVID-19 2) Level 3: Advanced Certificate in Public Procurement. 3) Level 4: Diploma in Strategic Public Procurement | Prof. Ibisime Etela (Procurement Officer) | To acquire skills for improved capacity in procurement towardds becoming global certfied procurement specialists | Improved procurement process for enhanced project delivery during and after COVID Pandemic and other possible future such situations | Within and outside Nigeria | 8000
6 | 1) Training on emerging trends in Financial Accounting and Forensic Practices. 2) Financial Accounting Responsibility | Mr. Maclin Noble (Project Auditor) | To deepen practical orientation in Accounting and Auditing with the requisite training for 21st Century Financial Accounts preparation and reporting | It will sharpen the skills of Accounting Practitioners and enhance their capacity to develop responsive Financial Accounting and Auditing | Within and outside Nigeria | 8000
7 | 1) Training on emerging trends in Financial Accounting and Forensic Practices. 2) Financial Accounting Responsibility | Dr. Benson P. Timah (Project Accountant) | To deepen practical orientation in Accounting with the requisite training for the 21st Century Financial Accounts preparation and reporting | It will sharpen the skills of Accounting Practitioners and enhance their capacity to develop responsive Financial Accounting and Auditing | Within and outside Nigeria | 8000
8 | Monitoring and evaluation (M&E) workshop for senior executives, government officials, development managers, and civil society that provides learning from past experiences, thereby improving service delivery, planning and allocating resources, and evaluating results for accountability | Mr. Uduma Ikpa (Monitoring and Evaluation Officer) | 1) To improve the operation and management of the ACE-CEFOR M&E function. 2) To improve the effectiveness of the ACE-CEFOR M&E process to help assess programme impacts | Improved M&E skills for high project impact during and after COVID Pandemic | Within and outside Nigeria | 8000
9 | 1) Communication, coordination and leadership for, effectively, communicating with stakeholders during and post COVID-19 Pandemic. 2) Developing and implementing strategic marketing plan | Mrs. Benedicta Omeni (Communication Officer/Secretary to Centre Leader) | To enhance leadership and supervisory skills for supporting ACE-CEFOR activities | Imcreased reputtation of ACE-CEFOR for doing business | Within and outside Nigeria | 8000
10 | 1) Managing projects for environmental, social and management plan compliance 2) Effective management of university-industry linkage for successful public-private partnership during and post COVID-19 Pandemic | Dr. Victor Joseph Aimikhe (Environmental and Social Safeguard Officer) | To enhance capacity for managing environmental and social issues from project implementation | Improved environmental and social impacts of prject | Within and outside Nigeria | 8000
11 | National Registry of Environmental Professionals (NREP), USA training and certification for faculty members and students | To be identified (selected faculty members and students) | To increase employability of participants | Trained and certified candidates become very marketable and employable upon graduation | ACE-CEFOR | 75000
12 | Organise short courses, attend short courses by steering committee members/other stakeholders like workshops and seminars in: 1) Effective laboratory management; 2) Principles and procedures for securing ISO Certification for laboratories in Higher Education Institutions; 3) HSE Training; 4) Skills and techniques for developing fundable grants and managing donor funded projects in Higher Education Institutions; 5) Capacity building for university-industry partnership towards efficient commercialisation of positive research results; 6) Developing a high performance and excellent team | To be identified (as nominated by partnering departments and organisations per session) | To contribute towards social and institutional impact of the ACE-CEFOR project | Contribute to the achievement of desired ACE-CEFOR development goals and ensure early warning and strategies for preventing failures | ACE-CEFOR | 50000
13 | Students and interns support through scholarship, research, publications, supervision, internship, conferences, seminars and workshops | To be identified (from students and interns) | To attend conferences/seminars/workshops; communicate research findings; students development, carry out research for innovation and publicity | Increased capabilities of students in the sub-region to adopt global best practices in research and training in Petroleum and related disciplines. and quality postgraduate education, knowledge transfer and internship programmes | To be determined | 195000
14 | Attend and participate at ACE Impact approved meetings | Only ACE-CEFOR Steering Committee members | To present progress reports and highlight ACE-CEFOR performance for visibility | Improved staff productivity and greater project impact | To be determined | 190000
15 | Other faculty members, other than steering committee members, and visiting scholars support for training, research, publications, supervision, internship, conferences, seminars and workshops | To be identified (from other faculty members and visiting scholars) | To attend conferences/seminars/workshops; communicate research findings; faculty members development, host visiting scholars, carry out research for innovation and publicity | Increased capabilities of faculty members in the sub-region to adopt global best practices in research and training in Petroleum and related disciplines. and quality postgraduate education, knowledge transfer and internship programmes | To be determined | 40655.39
16 | Sustain recognition as Regional Centre of Expertise (RCE) | Stakeholders from host communities for implementing sustainable development projects | Promote science education at all levels to enhance attainment of the UN Post-2015 Sustainable Development Goals (SDGs), better responses to socio-economic needs, and greener production processes in the petroleum and environmental studies sectors | Increased knowledge on new thinking in SDGs implementation for adoption of green technologies and chemicals for eco-friendly industry operations | To be determined | 40000
17 | Training support for CEFOR staff who provide critical administrative and auxilliary services like laboratory technicians, drivers, administrative staff, etc | To be identified (from administrative and auxilliary CEFOR staff) | To create a critical mass of personnel for sustaining the gains from the CEFOR imoacts | To enhance overall staff productivity and project impact through human capital development across all levels | To be determined | 15000
| Sub-Total |  |  |  |  | 689655.39
18 | Project management (10%) | For incidentals | To ensure minimum budgetted is used | To enhance project efficiency | On need-to-basis | 68965.539
[5 empty] | TOTAL | 758620.929
EXCHANGE RATE: ₦445 = U.S. $1

## Disbursement Plan
COUNTRY: NIGERIA
PROJECT: WORLD BANK AFRICA CENTRE OF EXCELLENCE PROJECT
CENTRE: AFRICA CENTRE OF EXCELLENCE IN OILFIELD CHEMICALS RESEARCH (ACE-CEFOR)
CREDIT NO: GRANT ID# - 60029544
DISBURSEMENT PLAN (JANUARY - DECEMBER, 2023)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | USD$ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 | Communication and marketing | CEFOR publicity | AMOUNT USD$: 35000; MONTHS MAR: 8000; MONTHS JUN: 9000; MONTHS SEP: 8000; MONTHS DEC: 10000; MONTHS TOTAL: 35000
2 | Teaching aids (MIS/LMS equipment | Efficient teaching | AMOUNT USD$: 150000; MONTHS MAR: 40000; MONTHS MAY: 40000; MONTHS AUG: 40000; MONTHS OCT: 30000; MONTHS TOTAL: 150000
3 | Books and journals: library hardware and software | Emhance learning and research | AMOUNT USD$: 70000; MONTHS FEB: 35000; MONTHS APR: 35000; MONTHS TOTAL: 70000
4 | 150 kVA Diesel Generator & maintenace | Good teaching & learning | 95000 | 2000 | 2000 | 2000 | 35000 | 40000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 95000
5 | Project vehicles maintenance | Facilitate CEFOR activities | 20000 | 1500 | 1500 | 1500 | 1500 | 1500 | 2000 | 2500 | 2000 | 1500 | 1500 | 1500 | 1500 | 20000
6 | Laboratory equipment with associated items | Improve learning and research | 230000 |  |  | 10000 | 10000 | 10000 | 70000 | 50000 | 50000 | 10000 | 10000 | 10000 |  | 230000
7 | Office, e-library and NgREN internet facilities | Support teaching and research | AMOUNT USD$: 250000; MONTHS APR: 100000; MONTHS JUN: 70000; MONTHS AUG: 40000; MONTHS SEP: 20000; MONTHS OCT: 20000; MONTHS TOTAL: 250000
8 | Provide e-facilities for Procurement, Accounting and Auditing | Proper Fiduciary Management | AMOUNT USD$: 150000; MONTHS FEB: 40000; MONTHS MAR: 40000; MONTHS APR: 35000; MONTHS MAY: 35000; MONTHS TOTAL: 150000
9 | Office Consumables | Quality Fiduciary Management | 40000 | 1500 | 4500 | 4000 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 40000
WORKS
10 | CEFOR Building extension and maintenance | Improve learning and research environment | 250000 | 10000 | 10000 | 10000 | 40000 | 40000 | 35000 | 35000 | 30000 | 10000 | 10000 | 10000 | 10000 | 250000
CONSULTANCY SERVICES
11 | Strategic Marketing: Develop research/patents/grants portal | Increase the visibility of CEFOR | AMOUNT USD$: 50000; MONTHS FEB: 2500; MONTHS MAY: 25000; MONTHS AUG: 2500; MONTHS NOV: 20000; MONTHS TOTAL: 50000
12 | Institutional Impact: NgReN Subscriptions | e-Journal access for partners | AMOUNT USD$: 100000; MONTHS FEB: 5000; MONTHS MAR: 5000; MONTHS APR: 45000; MONTHS MAY: 40000; MONTHS JUN: 5000; MONTHS TOTAL: 100000
13 | Annual Subscriptions to assocoiations / networks | Renewal of memberships | 100000 |  | 5000 | 25000 | 5000 | 5000 | 20000 | 5000 | 5000 | 20000 | 5000 | 5000 |  | 100000
14 | Accreditation and Gap analysis | International accreditation | AMOUNT USD$: 20000; MONTHS APR: 10000; MONTHS MAY: 10000; MONTHS TOTAL: 20000
OPERATING COST
15 | Students and interns support | Scholarship and internship | 195000 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 16250 | 195000
16 | Training other faculty members and visiting scholar | Train faculty members and scholars | 40655.39 | 3000 | 3000 | 4000 | 3000 | 3000 | 4655.39 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 40655.39
17 | National Registry of Environmental Professionals (NREP | Training and certification for faculty and students | AMOUNT USD$: 75000; MONTHS FEB: 40000; MONTHS MAR: 35000; MONTHS TOTAL: 75000
18 | Sustain recognition as Regional Centre of Expertise (RCE) | Promote sustainable development | AMOUNT USD$: 40000; MONTHS APR: 15000; MONTHS JUL: 15000; MONTHS OCT: 10000; MONTHS TOTAL: 40000
19 | Attend ACE meetings and relevant professional trainings | Participate at approved programmes | AMOUNT USD$: 274000; MONTHS MAR: 36000; MONTHS MAY: 100000; MONTHS JUL: 20000; MONTHS SEP: 18000; MONTHS NOV: 100000; MONTHS TOTAL: 274000
20 | Organise and attend short courses | Hold and attend short courses | AMOUNT USD$: 50000; MONTHS FEB: 10000; MONTHS APR: 10000; MONTHS JUN: 10000; MONTHS AUG: 10000; MONTHS OCT: 10000; MONTHS TOTAL: 50000
21 | Training support for CEFOR administrative and auxilliary staff | Administrative and auxilliary CEFOR staff | 15000 |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |  | 15000
OPERATING COST (PROJECT MANAGEMENT)
22 | Operating Cost (5% cost) | Project management | 112482.7695 | 1712.5 | 8812.5 | 11912.5 | 18262.5 | 18512.5 | 12470.2695 | 7662.5 | 10262.5 | 5762.5 | 6112.5 | 8612.5 | 2387.5 | 112482.7695
GRAND TOTAL
| TOTAL |  | 2362138.1595 | 35962.5 | 185062.5 | 250162.5 | 383512.5 | 388762.5 | 261875.6595 | 160912.5 | 215512.5 | 121012.5 | 128362.5 | 180862.5 | 50137.5 | 2362138.1595
EXCHANGE RATE: ₦445= U.S. $1