## 2024CEFORWorkplan
Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR)
Institution | University of Port Harcourt |  |  | On Schedule
Country | Nigeria
Center Leader | Professor Ikechukwu Agbagwa |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January 01-December 31, 2024
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Y2Q1 |  |  | 2024 Y2Q2 |  |  | 2024 Y2Q3 |  |  | 2024 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | [6 empty] | Comments
Action 1: Readiness \ DLI Action: 1
Sub-Action 1a: Basic Readiness
Activity 1: Prepare Workplan | Itemise planned activities for Year 2024 | [13 empty] | 1no 2024 Work Plan |  |  |  |  | Centre Leader
Activity 2: Prepare Procurement Plan | List potential contracts and procurements to achieve workplan | [13 empty] | 1no 2024 Procurement Plan |  |  |  |  | Procurement Officer
Activity 3: Prepare Financial Management Manual | State financial transactions and planned disbursements for 2024 | [13 empty] | 1no 2024 Financial Management Plan |  |  |  |  | Project Accountant
Sub-Action 1b: Full Readiness
Activity 1: Maintain ACE-CEFOR website & building | Promote visibility of Centre and her activities for Year 2024 | [13 empty] | Renew website and make building functional |  | 73230 |  |  | Procurement Officer
Activity 2: Maintain Statutory Advisory Board (SAB) | Strategic meetings to ensure Centre activities remain focused | [13 empty] | SAB Meetings & regional Committee training | Certification and training | 136181 |  |  | Centre Leader
Activity 3: Hold Project Implementation Meeting & Review | Necessary as part of team building and implementing project | [13 empty] | 8nos Project Implementation Meetings | Including stationery purchase | 60500 |  |  | Centre Leader
Action 2: Development Impact \ DLI Action: 2
Sub-Action 2a: Self-Assessment of Development Impact
Activity 1: Conduct self-assessment of development impact | Objective internal evaluation of activities for social impact | [13 empty] | 1no Self-assessment Report |  | 1000 |  |  | Centre Leader
Activity 2: Monitoring and Evaluation of project progress | Assess annual reports from Advisory Boards | [13 empty] | 4nos Monitoring & Evaluation Reports |  | 14000 |  |  | M & E Officer
Sub-Action 2b: Independent External Evaluation of Impact
Activity 1: Conduct independent external evaluation of impact | Independent external assessment of activities for social impact | [13 empty] | 1no Annual Report |  | 2000 |  |  | M & E Officer
Activity 2: Conduct tracer studies | Track graduates from Centre for employers ratings | [13 empty] | 1no Tracer Study |  | 5000 |  |  | M & E Officer
Activity 3: Organise Alumni homecoming for ACE-CEFOR | Opportunity to interact with CEFOR graduates for development | [13 empty] | 2nos Homecoming Event for Alumni |  | 10000 | 15000 |  | Centre Leader
Action 3: Quantity of Students \ DLI Action: 3
Sub-Action 3a: PhD Students
Activity 1: Organise project seminars for PhD students | Hold pre-data and post-data project seminars for PhD students | [13 empty] | 2nos PhD Seminars (proposal & pre-data) |  | 24000 |  |  | Centre Leader
Activity 2: Provide research support for PhD students | Advance research funds/grants to support PhD students projects | [13 empty] | Funding support for eligible PhD students |  | 42000 |  |  | Centre Leader
Activity 3: Present PhD students for defence (Administration & Logistics) | Hold viva voce for PhD students who have completed work | [13 empty] | PhD students defend thesis |  | 15000 |  |  | Centre Leader
Sub-Action 3b: Admit 20 MSc Students
Activity 1: Advertise and admit MSc students | Place adverts in, at least, two national dailies and website | [13 empty] | 1no Advert for national/regional MSc students | Global outreach consultancy | 4000 |  |  | Communication Officer
Activity 2: Organise orientation for MSc students | MSc Students have firsthand information about Centre | [13 empty] | 1no Orientation for new MSc students |  | 5000 |  |  | Centre Leader
Activity 3: Organise modular lectures for MSc students | MSc Students undertake lectures for prescribed courses | [13 empty] | Modular lectures for admitted MSc students |  | 21250 |  |  | Centre Leader
Activity 4: Organise project seminars for MSc students | Hold pre-data and post-data project seminars for MSc students | [13 empty] | 2nos MSc Seminars (proposal & pre-data) |  | 7875 |  |  | Centre Leader
Activity 5: Provide research support for MSc students | Advance research funds/grants to support MSc students projects | [13 empty] | Funding support for eligible MSc students |  | 20000 |  |  | Centre Leader
Activity 6: Present MSc students for defence (Administration & Logistics) | Hold viva voce for MSc students who have completed work | [13 empty] | MSc students defend dissertation |  | 5000 | 147141.56 |  | Centre Leader
Sub-Action 3c: Admit Short Course Students
Activity 1: Identify and mobilise faculty members & students | Receive nominations for faculty members & students | [13 empty] | 50nos Short course participants mobilised |  | 2600 |  |  | Centre Leader
Activity 2: Organise short course | Train nominated and accepted faculty members & students | [13 empty] | 20nos Short course participants trained |  | 2600 |  |  | Centre Leader
Activity 3: Train Steering Committee members | Capacity building for Steering Committee members in Nigeria | [13 empty] | 12nos Steering Committee members trained |  | 18000 |  |  | Centre Leader
Action 4: Quality of Education & Research \ DLI Action: 4
Sub-Action 4a: Accreditation of Course(s)
Activity 1: Introduce new or review existing course(s) | Create new course or review existing course at the Centre | [13 empty] | 1no New/Reviewed existing course |  | 10000 |  |  | Centre Leader
Activity 2: Secure international professional certification | Environmental/Safety Professional Certification for ACE-CEFOR PhD & MSc students and faculty members | [11 empty] | NREP Certification Completed |  | Certification for improved employability |  | 40000 |  |  | Centre Leader
Sub-Action 4b: Conduct Applied Research in Oilfield Chemicals
Activity 1: Identify and approve applied research | Select appropriate applied research for approval and support | [13 empty] | 6nos innovative proposal review meetings |  | 5000 | 300000 |  | Centre Leader
Activity 2: Provide funding support in cash and or kind | Solicit possible funding support for approved applied research | [13 empty] | 20nos innovative applied researches supported |  | 50000 |  |  | Centre Leader
Activity 3: Sustain recognition as Regional Centre of Expertise | Stakeholders meetings & identify innovative applied researches | [13 empty] | 2nos Stakeholders Meeting; 2nos Conference |  | 10000 |  |  | Procurement Officer
Activity 4: Support training, workshop/conference attendance | Fund participant to training, workshop and conference | [13 empty] | 20nos participants from funded projects |  | 10000 |  |  | Centre Leader
Activity 5: Prepare manuscripts & publish results | Support relevant applied research and publish quality papers | [13 empty] | 20nos quality applied research papers |  | 20000 | 350000 |  | Centre Leader
Activity 6: Attend ACE Impact Project Regional workshops & other meetings | Steering Committee members attend approved project meetings | [13 empty] | 2nos Project Review Workshops attended |  | 150000 |  |  | Centre Leader
Sub-Action 4c: Infrastructure Improvement
Activity 1: Maintenance of existing infrastructure | Award and implement office extension at CEFOR | [13 empty] | Maintenance of existing infrastructure |  | 52500 |  |  | Procurement Officer
Action 5: Relevance of Education & Research \ DLI Action: 5
Sub-Action 5a: Generate External Revenue
Activity 1: Secure external funding from regional sources | Amount of grant secured from external sources in the region | Grants and donations from partner institutes and centres | [12 empty] | External revenue generated (regional) |  | 170000 |  | 200000 | Centre Leader
Activity 2: Secure external funding from national sources | Amount of grants secured from external sources in Nigeria | Additional support | [12 empty] | External revenue generated (national) |  | 200000 | 220000 |  | Centre Leader
Sub-Action 5b: Organise 1-Month Internships
Activity 1: Organise Sectoral Advisory Board meeting | Convene SAB meeting for CEFOR | [13 empty] | 1no Sectoral Advisory Board meeting |  | 5000 |  |  | Centre Leader
Activity 2: Organise International Scientific Advisory Board | Convene International Scientific Advisory Board meeting | [13 empty] | 1no International Scientific Advisory Board |  | 8500 |  |  | Centre Leader
Activity 3: Assign and post qualified interns to relevant industry | Enter MoU & place students on 1-month industrial internship | [13 empty] | 15nos students undertake 1-month internship |  | 15000 | 25000 |  | Industry Liaison Officer
Sub-Action 5c: Technology Incubation & Commercialisation Process
Activity 1: Identify and review technology for incubation | Appraise positive results from ongoing or completed researches | [13 empty] | Technology for innovation identified |  | 5000 |  |  | Centre Leader
Activity 2: Initiate patenting process for commercialisation | Patent or commercialise good quality research outputs | [13 empty] | Engage in patenting & commercialisation process |  | 10000 | 150000 |  | Centre Leader
Action 6: Timeliness & Quality of Fiduciary Management \ DLI Action: 6
Activity 1: Prepare fiduciary report | Prepare and submit fiduciary report |  |  | Report Submitted | [5 empty] | Report Submitted |  |  |  |  | 1no fiduciary report submitted |  | 5000 | 55252 |  | Project Accountant
Activity 2: Conduct oversight internal audit by committee | Prepare and submit Internal Audit Report |  |  | Report Submitted | [5 empty] | Report Submitted |  |  |  |  | 1no Internal Audit Report submitted |  | 5000 | 60027 |  | Project Auditor
Activity 3: Publish centre expenditure on website | Publish Centre’s Expenditure Report on website | [13 empty] | 1no Expenditure Report placed on website |  | 5000 | 20464 |  | M & E Officer
Activity 4: Prepare procurement plan | Publish Centre’s Procurement Report on website | [13 empty] | 1no Procurement Report placed on website |  | 5000 |  |  | Procurement Officer
Action 7: Institutional Impact \ DLI Action: 7
Sub-Action 7a: UniPort university-wide regional strategy
Activity 1: Engage stakeholders for MoUs / Develop strategy | Produce strategy document with relevant stakeholders | [13 empty] | 1no New/Reviewed MoU |  | 6214 |  |  | Centre Leader
Activity 2: Prepare and publish university-wide strategy book | Produce and circulate university-wide strategy document | [13 empty] | Complete university-wide strategy document |  | 10000 |  |  | Centre Leader
Sub-Action 7b: Merit-based Selection of Officers
Activity 1: Assess VC selection process for openness/merit | Ascertain wether or not VC selection process if merit-based | [13 empty] | 1no VC selection method report |  | 2000 |  |  | M & E Officer
Activity 2: Assess Dean selection process for openness/merit | Ascertain wether or not Dean selection process if merit-based | [13 empty] | 1no Dean selection method report |  | 1000 |  |  | M & E Officer
Sub-Action 7c: Institutional ISO Certification
Activity 1: ISO certification | Institution gets international accreditation & ISO Certification | [11 empty] | Certification Completed |  | Initiate ISO Certification process |  | 10000 |  |  | Centre Leader
Sub-Action 7d: PASET Benchmarking & Intervention Plan
Activity 1: Apply for PASET Benchmarking exercise | Centre campaigns for PASET organised program | [13 empty] | 1no PASET Benchmarking Report |  | 10000 |  |  | Centre Leader
Activity 2: Participate and submit PASET Intervention Plan | Centre participates in PASET call for grants application(s) | [13 empty] | 1no Application for PASET support grant |  | 10000 | 100000 |  | Centre Leader
Sub-Action 7e: Milestone on Institutional Impact
Activity 1: Engage UniPort Foundation for agreed intervention | Centre supports UniPort to implement agreed intervention | [13 empty] | Project to be implemented identified |  | 5000 |  |  | Centre Leader
Activity 2: Facilitate a university-wide function in UniPort (Innovation Week; Etc) | Centre to provide support for a university-wide function | [13 empty] | 1no university-wide function implemented |  | 30000 | 100000 |  | Centre Leader
Sub-Action 7f: ICT for Innovation in Teaching & Research
Activity 1: Conduct scoping study of areas to extend ICT to | Centre to access areas yet to enjoy internet cover | [13 empty] | University sections for ICT extension identified |  | 2000 |  |  | Centre Leader
Activity 2: Extend ICT for teaching and research to need areas | Extend ICT facility including NgREN to all parts on UniPort | [13 empty] | ICT facilities provided at new locations |  | 12800 | 100000 |  | Procurement Officer
[16 empty] | GRAND TOTAL | 1349250 | 1642884.56 | 200000
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus