## 2025CEFORWorkplan
Name of Center | World Bank Africa Centre of Excellence (ACE) in Oilfield Chemicals Research (ACE-CEFOR)
Institution | University of Port Harcourt |  |  | On Schedule
Country | Nigeria
Center Leader | Professor Ikechukwu Agbagwa |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January 01-June 30, 2025
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y2Q1 |  |  | 2025 Y2Q2 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | [6 empty] | Comments
Action 1: Readiness \ DLI Action: 1
Sub-Action 1a: Basic Readiness
Activity 1: Prepare Workplan | Itemise planned activities for Year 2025 | [7 empty] | 1no 2025 Work Plan |  |  |  |  | Centre Leader
Activity 2: Prepare Procurement Plan | List potential contracts and procurements to achieve workplan | [7 empty] | 1no 2025 Procurement Plan |  |  |  |  | Procurement Officer
Activity 3: Prepare Financial Management Manual | State financial transactions and planned disbursements for 2025 | [7 empty] | 1no 2025 Financial Management Plan |  |  |  |  | Project Accountant
Sub-Action 1b: Full Readiness
Activity 1: Maintain ACE-CEFOR website | Promote visibility of Centre and her activities for Year 2025 | [7 empty] | Renew website Subscription |  | 9150 |  |  | Procurement Officer
Activity 2: Maintain Statutory Advisory Board (SAB) | Strategic meetings to ensure Centre activities remain focused | [7 empty] | SAB Meetings |  | 5000 |  |  | Centre Leader
Action 2: Development Impact \ DLI Action: 2
Sub-Action 2a: Self-Assessment of Development Impact
Activity 1: Conduct self-assessment of development impact | Objective internal evaluation of activities for social impact | [7 empty] | 1no Self-assessment Report |  | 1000 |  |  | Centre Leader
Activity 2: Monitoring and Evaluation of project progress | Completion of Self-Assessment Activities | [7 empty] | 1no Self-assessment Report |  | 5000 |  |  | M & E Officer
Sub-Action 2b: Independent External Evaluation of Impact
Activity 1: Conduct independent external evaluation of impact | Independent external assessment of activities for social impact | [7 empty] | 1no Report |  | 2000 |  |  | M & E Officer
Activity 2: Conduct tracer studies | Track graduates from Centre for employers ratings | [7 empty] | 1no Tracer Study |  | 5000 |  |  | M & E Officer
Activity 3: Organise Alumni homecoming for ACE-CEFOR | Opportunity to interact with CEFOR graduates for development | [7 empty] | 1no Homecoming Event for Alumni |  | 10000 | 15000 |  | Centre Leader
Action 3: Quantity of Students \ DLI Action: 3
Sub-Action 3a: PhD Students
Activity 1: Organise project seminars for PhD students | Hold pre-data and post-data project seminars for PhD students | [7 empty] | 2nos PhD Seminars (proposal & pre-data) |  | 10000 |  |  | Centre Leader
Activity 2: Provide research support for PhD students | Advance research funds/grants to support PhD students projects | [7 empty] | Funding support for eligible PhD students |  | 20000 |  |  | Centre Leader
Activity 3: Present PhD students for defence (Administration & Logistics) | Hold viva voce for PhD students who have completed work | [7 empty] | PhD students defend thesis |  | 10000 |  |  | Centre Leader
Sub-Action 3b: Admit 20 MSc Students
Activity 1: Organise orientation for MSc students | MSc Students have firsthand information about Centre | [7 empty] | 1no Orientation for new MSc students |  | 1000 |  |  | Centre Leader
Activity 2: Organise modular lectures for MSc students | MSc Students undertake lectures for prescribed courses | [7 empty] | Modular lectures for admitted MSc students |  | 10000 |  |  | Centre Leader
Activity 3: Organise project seminars for MSc students | Hold pre-data and post-data project seminars for MSc students | [7 empty] | 2nos MSc Seminars (proposal & pre-data) |  | 5000 |  |  | Centre Leader
Activity 4: Provide research support for MSc students | Advance research funds/grants to support MSc students projects | [7 empty] | Funding support for eligible MSc students |  | 20000 |  |  | Centre Leader
Action 4: Quality of Education & Research \ DLI Action: 4
Sub-Action 4a: Conduct Applied Research in Oilfield Chemicals
Activity 1: Identify and approve applied research | Select appropriate applied research for approval and support | [7 empty] | 6nos innovative proposal review meetings |  | 5000 | 300000 |  | Centre Leader
Activity 2: Support training, workshop/conference attendance | Fund participant to training, workshop and conference | [7 empty] | 5nos participants from funded projects |  | 10000 |  |  | Centre Leader
Activity 3: Prepare manuscripts & publish technical papers | Support relevant applied research and publish quality papers | [7 empty] | 20nos quality applied research papers |  | 4000 | 180000 |  | Centre Leader
Activity 4: Attend ACE Impact Project Regional workshops & other meetings | Steering Committee members attend approved project meetings | [7 empty] | 1nos Project Review Workshops attended |  | 27000 |  |  | Centre Leader
Sub-Action 4b: Infrastructure Improvement
Activity 1: Maintenance of existing infrastructure | Maintenance of existing infrastructure | [7 empty] | Maintenance of existing infrastructure |  | 15000 |  |  | Procurement Officer
Action 5: Relevance of Education & Research \ DLI Action: 5
Sub-Action 5a: Generate External Revenue
Activity 1: Secure external funding from regional sources | Amount of grant secured from external sources in the region | Grants and donations from partner institutes and centres | [6 empty] | External revenue generated (regional) |  | 3000 | 150000 | 200000 | Centre Leader
Activity 2: Secure external funding from national sources | Amount of grants secured from external sources in Nigeria | Additional support | [6 empty] | External revenue generated (national) |  | 1000 | 220000 |  | Centre Leader
Sub-Action 5b: Organise Advisory Board Meetings
Activity 1: Organise Sectoral Advisory Board meeting | Convene SAB meeting for CEFOR | [7 empty] | 1no Sectoral Advisory Board meeting |  | 2000 |  |  | Centre Leader
Activity 2: Organise International Scientific Advisory Board | Convene International Scientific Advisory Board meeting | [7 empty] | 1no International Scientific Advisory Board |  | 3000 |  |  | Centre Leader
Sub-Action 5c: Technology Incubation & Commercialisation Process
Activity 1: Identify and review technology for incubation | Appraise positive results from ongoing or completed researches | [7 empty] | Technology for innovation identified |  | 5000 |  |  | Centre Leader
Activity 2: Initiate patenting process for commercialisation | Patent or commercialise good quality research outputs | [7 empty] | Engage in patenting & commercialisation process |  | 10000 | 150000 |  | Centre Leader
Action 6: Project Closure activities/ Timeliness & Quality of Fiduciary Management \ DLI Action: 6
Activity 1: Prepare fiduciary report | Prepare and submit fiduciary report | [7 empty] | 1no fiduciary report submitted |  | 2000 |  |  | Project Accountant
Activity 2: Conduct oversight internal audit by committee | Prepare and submit Internal and Expernal Audit Report | [7 empty] | 1no Internal Audit Report submitted |  | 2000 |  |  | Project Auditor
Activity 3: Publish centre expenditure on website | Publish Centre’s Expenditure Report on website | [7 empty] | 1no Expenditure Report placed on website |  | 1000 |  |  | M & E Officer
Activity 4: Prepare procurement report | Publish Centre’s Procurement Report on website | [7 empty] | 1no Procurement Report placed on website |  | 1000 |  |  | Procurement Officer
Activity 5: Project Completion Report, ACE @10 Activities, closeout ceremony | Documentary, final financial reporting, documentation and project completion report | [7 empty] | Project Completion Report, etc |  | 15000 |  |  | Centre Leader
Action 7: Institutional Impact \ DLI Action: 7
Sub-Action 7a: Milestone on Institutional Impact
Activity 1: Equipping of Laboratory | Laboratory equipment and associated furniture, reagents, maintenance/lab staff training | [7 empty] | ACE-CEFOR Laboratory to be further equipped |  | 95000
Sub-Action 7b: ICT for Innovation in Teaching & Research
Activity 1: Maintain ICT for teaching and research to needed areas | Maintain ICT facility including NgREN in all parts on UniPort | [7 empty] | Maintenance and subscription to NgReN Activities |  | 25000 | 100000 |  | Procurement Officer
[10 empty] | GRAND TOTAL | 339150 | 1115000 | 200000
Note on N6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus